## Activities
heyo | WP | activity name | Start Month | End Month/ Planned End Date | Single/Inter/Trans-disciplinary
1 | 1 | Blackstairs GWS micro-hydropower installation | 1 | 33 | Transdisciplinary
2 | 1 | Ty Mawr Wybrnant GWS micro-hydropower installation | 1 | 39 | Transdisciplinary
3 | 1 | A model for the extrapolation of the characteristic curves of Pumps as Turbines from a datum Best Efficiency Point | 1 | 26 | Single Discipline
4 | 1 | BGWS Primary School Webinars | 57 | 64 | Transdisciplinary
5 | 1 | Cost model for pumps as turbines in run-of-river and in-pipe microhydropower applications | 1 | 33 | Single Discipline
6 | 1 | Sustainability Webinar on MHP | 54 | 54 | Interdisciplinary
7 | 1 | Design and Year-Long Performance Evaluation of a Pump as Turbine (PAT) Pico-Hydropower Energy Recovery Device in a Water Network | 38 | 62
8 | 1 | Monitoring and maintaining of the Demonstration sites in Ty Mawr and Blackstairs | 33 | 78
9 | 2 | Decentralized drain water heat recovery: A probabilistic method for prediction of wastewater and heating system interaction | 1 | 29
10 | 2 | Decentralized drain water heat recovery from commercial kitchens in the hospitality sector. | 1 | 35
11 | 2 | Spatial and temporal considerations in the performance of wastewater heat recovery systems | 1 | 40
12 | 2 | Design and implementation of DWHR system at Penrhyn Castle | 1 | 42 | Transdisciplinary
13 | 2 | Ongoing functioning and monitoring of Penrhyn Castle heat recovery system | 42 | 78 | Interdisciplinary
14 | 4 | Webinar: Don't flush money down the kitchen drain! How to recover heat from drain water in commercial kitchens and save costs and emissions. | 55 | 55 | Interdisciplinary
15 | 4 | Heat recovery toolkit | 31 | 55 | Interdisciplinary
16 | 4 | Emissions down the drain: Balancing life cycle energy and greenhouse gas savings with resource use for heat recovery from kitchen drains | 23 | 47 | Interdisciplinary
17 | 4 | Circular use of feed by-products from alcohol production mitigates water scarcity | 35 | 64 | Single Discipline
18 | 4 | Heat recovery and water reuse in micro-distilleries improves eco-efficiency of alcohol production | 31 | 74 | Interdisciplinary
20 | 7 | Webinar: Impacts of climate change on future water availability for hydropower and public water supply in Wales, UK | 62 | 62 | Transdisciplinary
21 | 7 | Climate change impact assessment for UK and Irish hydropower production | 53 | 78 | Single Discipline
22 | 7 | Historical climate and streamflow characterisation study for Wales, with publication | 1 | 18 | Single Discipline
23 | 7 | Climate change impact study for future streamflow and water quality in Wales, with publication | 19 | 52 | Single Discipline
24 | 7 | Climate change impact assessment study of water resources for hydropower and public water supply in Wales, with publication | 18 | 47 | Single Discipline
25 | 8 | Primary School Webinars (BGWS) | 57 | 64 | Transdisciplinary
26 | 8 | Implementation of demonstration sites: Blackstairs GWS (IRL); Ty Mwr Wybrant (Wales, UK); Penrhyn Castle (Wales, UK) and ABP Foods (IRL) | 1 | 78 | Transdisciplinary
27 | 8 | Tŷ Mawr Wybrnant Pico Hydropower Demonstration Site Launch | 39 | 39 | Transdisciplinary
28 | 8 | Establishment of a Smart Specialisation Cluster and Water-Energy Network | 1 | 78 | Transdisciplinary
29 | 8 | Communication activities: project website; newsletters; Social media: Twitter;Youtube; LinkedIn | 1 | 78 | Interdisciplinary
30 | 8 | Sustainability Webinar Series | 54 | 78 | Interdisciplinary
31 | 8 | Launch of Blackstairs Demonstration site | 33 | 33 | Transdisciplinary
32 | 8 | NTW staff engagement and training about the heat recovery system and Penrhyn | 62 | 78
33 | 8 | Visitors engagement with Penrhyn Castle Heat recovery system | 62 | 78
34 | 8 | All DU activities: technological solutions; energy and environmental audits and assessments; climate change impact assessment; action learning activities and communication methods | 1 | 52 | Interdisciplinary
35 | 3 | EPANET workshop for NFGWS | 63 | 63
36 | 6 | Improving water-related energy efficiency in wet leisure centres in Denbighshire County Council (DCC). | 30 | 42 | Interdisciplinary
37 | 6 | Expert panel discussion on heat recovery potential of leisure centres. | 54 | 54 | Transdisciplinary
38 | 6 | Heat recovery potential of leisure centres (Calon Tysul leisure centre - Ceredigion). | 43 | 78 | Interdisciplinary
39 | 6 | Water-energy efficiency of commercial swimming pools (6 x Welsh leisure centres in collaboration with Pool Sentry). | 43 | 70 | Transdisciplinary
40 | 6 | Water-energy efficiency in offices (M-Sparc: Menai Science Park). | 43 | 49 | Interdisciplinary
41 | 6 | Water-energy efficiency of Gibney's pub in Dublin | 55 | 78 | Interdisciplinary
42 | 8 | NFGWS Primary School Workshops | 67 | 78 | Transdisciplinary
43 | 2 | Drain Water Heat Recovery Webinar | 55 | 55 | Transdisciplinary
44 | 2 | Grease Trap Heat recovery device development | 61 | 78 | Single Discipline
45 | 2 | Design and Implementation of ABP Food demonstration site | 21 | 78 | Transdisciplinary
46 | 2 | ABP Food monitoring | 41 | 78 | Transdisciplinary
47 | 5 | Benchmarking Webinar | 56 | 56 | Interdisciplinary
48 | 2 | Bangor University Student Accommodation monitoring | 65 | 78 | Transdisciplinary
49 | 2 | Monitoring of the Rediscovery Centre grease trap and feasibility report for DWHR | 64 | 64 | Transdisciplinary
50 | 4 | Webinar: Don't flush money down the kitchen drain! How to recover heat from drain water in commercial kitchens and save costs and emissions. Heat Recovery Tool Webinar- 2 | 68 | 68 | Interdisciplinary
51 | 8 | Kick-Off meeting | 2 | 2 | Transdisciplinary
52 | 8 | First Annual Conference: 'Sustainability in Energy & Water Resources: Research & Practice' , 27 October 2017 | 14 | 14 | Transdisciplinary
53 | 8 | Enhancing the Resilience of your Welsh Organisation: Achieving Water and Energy Savings, 26 Feb 2018 | 18 | 18 | Transdisciplinary
54 | 8 | Water & Energy in Rural Communities. A workshop for Group Water Schemes in Ireland, 26 April 2018 | 20 | 20 | Transdisciplinary
55 | 8 | Second Annual Conference: ' Water-Energy Innovation'. 23 October 2018 | 26 | 26 | Transdisciplinary
56 | 6 | Climate action hackathon programme in Welsh secondary schools | 65 | 78 | Interdisciplinary
57 | 6 | Citizen science project in Irish homes | 60 | 78 | Interdisciplinary
58 | 8 | Engagement Event - Citizen Science Project on Water-Energy Efficiency in Irish Households | 58 | 60 | Interdisciplinary
59 | 8 | Climate Action Hackathon with ECO-UNESCO | 56 | 58 | Interdisciplinary
60 | 2 | Decentralized vs centralized WWHR | 53 | 78 | Single Discipline
61 | 6 | Improving water-related energy efficiency in wet leisure centres in Denbighshire County Council (DCC). | 30 | 42
62 | 6 | Improving water-related energy efficiency in Denbighshire (DCC) Primary schools.
63 | 7 | Climate change impact assessment for UK and Irish hydropower production | 19 | 52
64 | 8 | Developing green process innovation through network action learning journal article submission to Creativity & Innovation Management | 46 | 66 | Interdisciplinary
65 | 4 | Reducing household greenhouse gas emissions from space and water heating through low-carbon technology: Identifying cost-effective approaches | 50 | 62
66 | 8 | Climate Action Hackathon Programme in Irish Secondary School - Focus Group | 67 | 68 | Transdisciplinary
67 | 5 | Economic and environmental efficiency of UK and Ireland water companies: Influence of exogenous factors and rurality | 14 | 35 | Interdisciplinary
68 | 5 | Key performance indicators to explain energy & economic efficiency across water utilities, and identifying suitable proxies | 36 | 49 | Interdisciplinary
69 | 5 | Aligning efficiency benchmarking with sustainable outcomes in the United Kingdom water sector | 50 | 58 | Interdisciplinary
70 | 5 | Pitfalls in international benchmarking of energy intensity across wastewater treatment utilities | 59 | 64 | Single Discipline
71 | 5 | Cross-sector sustainability benchmarking of major utilities in the United Kingdom | 65 | 74 | Interdisciplinary
72 | 1 | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Ballacolla network | 6 | 9 | Single Discipline
73 | 1 | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Blackstairs network | 6 | 9 | Single Discipline
74 | 1 | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Ballinabrannagh network | 6 | 9 | Single Discipline
75 | 1 | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Kilanerin network | 6 | 9 | Single Discipline
76 | 1 | EPS Hydropower Potential Feasibility Assessment: Drogheda WWTP, Blackstairs WTP, Cork Lower Harbour | 9 | 11 | Single Discipline
77 | 1 | Hydro Project Blaenau Gwent Pre feasibility study | 12 | 13 | Single Discipline
78 | 1 | Five Fords Hydropower site - Preliminary design | 1 | 3 | Single Discipline
79 | 1 | Dublin City Council Hydropower potential feasibility assessment Dodder Water Supply Scheme | 21 | 22 | Single Discipline
80 | 1 | Preliminary design of a hydropower energy recovery scheme Case study: Rathnure tank inlet | 12 | 14 | Single Discipline
81 | 1 | Tara Mines hydro feasibility assessment | 45 | 47 | Single Discipline
82 | 1 | Dairygold WWTP hydro feasibility assessment | 41 | 43 | Single Discipline
83 | 1 | Fethard WTP hydro feasibility assessment | 43 | 44 | Single Discipline
84 | 4 | Introducing a Calculator for the Environmental and Financial Potential of DrainWater Heat Recovery in Commercial Kitchens | 31 | 64 | Interdisciplinary
85 | 2 | Imperial Hotel DWHR Assessment | 65 | 78 | Transdisciplinary
86 | 7 | Study on the impact of variation in abstraction licence conditions between England, Wales, Scotland, Northern Ireland, and Ireland on water abstraction for run-of-river hydropower | 65 | 78 | Single Discipline
87 | 7 | Consultation and modelling work for Talybont Community Flood Group constituting an assessment of sub-basin contributions to peak flows at Talybont in the Afon Leri catchment, and the potential impact of tree planting on streamflow. | 56 | 57 | Transdisciplinary
88 | 4 | Carbon, water footprint and heat recovery assessment for Aber Falls distillery and consultation on how environmental footprint can be reduced. | 69 | 71 | Transdisciplinary
89 | 8 | Launch of Penrhyn Demonstration site in person | 74 | 74
90 | 8 | Launch of Penrhyn Demonstration site online | 74 | 74
91 | 8 | 3D tours of demonstration sites | 68
92 | 2 | Drain Water Heat Recovery Fesibility Studies | 16 | 44
93 | 5 | GIS and water industry statistic based study to explore the effect of rurality on energy consumption in water supply services | 25 | 25
94 | 1 | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case studies: Ballinguiroe Tankardstown GWS, Coolagh Caherleske GWS, Kilcredan GWS, Killally Ballinrush GWS and Kilriffith Kilmore GWS and Walterstown (plus Moyne and Patrickswell GWSs - unfinished) | 15 | 20 | Single Discipline
95 | 1 | Mullins Mill, Kells, County Kilkenny Hydropower potential assessment | 25 | 25 | Single Discipline
96 | 8 | Climate Action Hackathon Programme in Irish Secondary School - Delivery | 75 | 78
97 | 4 | Studying water, energy and material use as well as energy and resource recovery options in a micro-distillery, focussing on by-product streams and water heat recovery. | 25 | 75 | Inter- and Transdisciplinary
98 | 7 | Hydrological modelling assessment in the Afon Gwyrfai catchment to quantify flooding impacts | 22 | 22
99 | 1 | Preliminary design of a 4KWh pico hydro scheme powered by a pump-as-turbine for Ogwen Hydro | 10 | 10

## work packages
id | category | SDG_1 | SDG_2 | SDG_3 | SDG_4 | SDG_5 | SDG_6 | SDG_7 | SDG_8 | SDG_9 | SDG_10 | SDG_11 | SDG_12 | SDG_13 | SDG_14 | SDG_15 | SDG_16 | SDG_17
wp1 | Technology platfroms | [5 empty] | 1 | 1 | 1 | 1 |  | 1 | [5 empty] | 1
wp2 | Technology platfroms | [5 empty] | 1 | 1 | 1 | 1 |  |  | 1 |  |  |  |  | 1
wp3 | Technology platfroms | [5 empty] | 1 | 1 |  | 1 |  | 1
wp4 | Policy Support and Guidance | [5 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 |  | 1 | 1 |  | 1
wp5 | Policy Support and Guidance | [5 empty] | 1 | 1 | 1 | 1
wp6 | Policy Support and Guidance | [5 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  |  |  | 1
wp7 | Policy Support and Guidance | [5 empty] | 1 | 1 | [5 empty] | 1
wp8 | Dissemination and Collaboration |  |  |  | 1 |  | 1 | 1 |  |  | 1 |  |  | 1 | 1 | 1 |  | 1

## stakeholders
|  | Sector | Enterprise Category | Assign Level of engagement (0-none; 1-inform; 2 consult; 3-share; 4- cocreate) to stakeholders who participating
| Start Month |  |  | 2 | 14 | 18 | 20 | 26 | 33 | 39 | 63 | 60 | 54 | 54 | 55 | 55 | 56 | 62 | 68 | 12 |  |  | 1 | 1 | 67 | 57 | 67 | 56 | 69 | [8 empty] | 12 |  |  |  |  | 64 | [5 empty] | 65 | [7 empty] | 75 |  |  | 10
| Activity Name |  |  | Kick-Off meeting | First Annual Conference: 'Sustainability in Energy & Water Resources: Research & Practice' , 27 October 2017 | Enhancing the Resilience of your Welsh Organisation: Achieving Water and Energy Savings, 26 Feb 2018 | Water & Energy in Rural Communities. A workshop for Group Water Schemes in Ireland, 26 April 2018 | Second Annual Conference: ' Water-Energy Innovation'. 23 October 2018 | Launch of Blackstairs Demonstration site | T? Mawr Wybrnant Pico Hydropower Demonstration Site Launch | EPANET | Engagement Event - Citizen Science Project on Water-Energy Efficiency in Irish Households | Expert panel discussion on heat recovery potential of leisure centres | Sustainability Webinar on MHP | Drain Water Heat Recovery Webinar | Heat recovery in commercial kitchens Webinar | Benchmarking Webinar | Webinar: Impacts of climate change on future water availability for hydropower and public water supply in Wales, UK | Heat Recovery Tool Webinar- 2 | Blackstairs GWS micro-hydropower installation | Design and Implementation of ABP Food demonstration site | ABP Food monitoring | Ty Mawr Wybrnant GWS micro-hydropower installation | Design and implementation of DWHR system at Penrhyn Castle | NFGWS Primary School Workshops | Primary School Webinars (BGWS) | Climate Action Hackathon Programme in Irish Secondary School - Focus Group | Climate Action Hackathon with ECO-UNESCO | Carbon, water footprint and heat recovery assessment for Aber Falls distillery and consultation on how environmental footprint can be reduced. | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Ballacolla network | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Blackstairs network | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Ballinabrannagh network | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Kilanerin network | EPS Hydropower Potential Feasibility Assessment: Drogheda WWTP, Blackstairs WTP, Cork Lower Harbour | Hydro Project Blaenau Gwent Pre feasibility study | Five Fords Hydropower site - Preliminary design | Dublin City Council Hydropower potential feasibility assessment Dodder Water Supply Scheme | Preliminary design of a hydropower energy recovery scheme Case study: Rathnure tank inlet | Tara Mines hydro feasibility assessment | Dairygold WWTP hydro feasibility assessment | Fethard WTP hydro feasibility assessment | Imperial Hotel DWHR Assessment | Monitoring of the Rediscovery Centre grease trap and feasibility report for DWHR | Improving water-related energy efficiency in wet leisure centres in Denbighshire County Council (DCC). | Heat recovery potential of leisure centres (Calon Tysul leisure centre - Ceredigion). | Water-energy efficiency of commercial swimming pools (6 x Welsh leisure centres in collaboration with Pool Sentry). | Water-energy efficiency in offices (M-Sparc: Menai Science Park). | Water-energy efficiency of Gibney's pub in Dublin | Bangor University Student Accommodation monitoring | Consultation and modelling work for Talybont Community Flood Group constituting an assessment of sub-basin contributions to peak flows at Talybont in the Afon Leri catchment, and the potential impact of tree planting on streamflow. | Launch of Penrhyn Demonstration site in person | Launch of Penrhyn Demonstration site online | Drain Water Heat Recovery Fesibility Studies | GIS and water industry statistic based study to explore the effect of rurality on energy consumption in water supply services | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case studies: Ballinguiroe Tankardstown GWS, Coolagh Caherleske GWS, Kilcredan GWS, Killally Ballinrush GWS and Kilriffith Kilmore GWS and Walterstown GWS (plus Moyne and Patrickswell GWSs - unfinished) | Mullins Mill, Kells, County Kilkenny Hydropower potential assessment | Climate Action Hackathon Programme in Irish Secondary School - Delivery | Studying water, energy and material use as well as energy and resource recovery options in a micro-distillery, focussing on by-product streams and water heat recovery. | Hydrological modelling assessment in the Afon Gwyrfai catchment to quantify flooding impacts | Preliminary design of a 4KWh pico hydro scheme powered by a pump-as-turbine
S_ID | Organisation/Activity ID |  |  | 51 | 52 | 53 | 54 | 55 | 31 | 27 | 35 | 58 | 37 | 6 | 43 | 14 | 47 | 20 | 50 | 1 | 45 | 46 | 2 | 12 | 42 | 25 | 66 | 59 | 88 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 85 | 49 | 36 | 38 | 39 | 40 | 41 | 48 | 87 | 89 | 90 | 92 | 93 | 93 | 95 | 96 | 97 | 98 | 99
S_1 | 9 Meals From Anarchy | Industry | Food | [11 empty] | 2
S_2 | Aber falls distillery | Industry | Beverage | [25 empty] | 3
S_3 | ABP Food Group | Industry | Food |  |  |  |  | 2 | [12 empty] | 3 | 3 | [30 empty] | 2
S_4 | Action Renewables | Professional, administration and support services | Consultancy |  | 3 |  |  | 2 | [43 empty] | 2
S_5 | Adnams Brewery and Distillery | Industry | Beverage | 3 | 3
S_6 | AEC | No-profit institution | Professional Association |  |  |  |  | 2
S_7 | Aramark Northern Europe | Professional, administration and support services | Customer services |  |  |  |  | 2
S_8 | ARUP | Professional, administration and support services | ARUP |  | 3 |  | 2
S_9 | Ashlawn Nursing Home | Health care | Ashlawn Nursing Home | [49 empty] | 2
S_10 | Auralab | Professional, administration and support services | Auralab | 3
S_12 | Ballinabranna Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2 | [13 empty] | 4 | [6 empty] | 2
S_14 | Ballingate Group Water Scheme | Utility | Water provider | [5 empty] | 3
S_15 | Ballinguiroe Tankardstown GWS | Utility | Water provider | [51 empty] | 2
S_16 | Ballyshannon Leisure Centre | Sport Facilities | Ballyshannon Leisure Centre | [9 empty] | 3
S_19 | Birchfield Farm | Agriculture | Birchfield Farm |  |  | 3
S_20 | Black & Veatch | Professional, administration and support services | Consultancy | [50 empty] | 3
S_21 | Black Boy Inn | Hospitality | Black Boy Inn | [12 empty] | 2
S_22 | Blackstairs Group Water Scheme | Utility | Water provider |  |  |  | 2 | 2 | 3 |  | 2 | [8 empty] | 4 |  |  |  |  | 4 | 4 |  |  |  |  | 2
S_23 | Blaen Eidda Ysbyty Ifan | Agriculture | Blaen Eidda Ysbyty Ifan | [6 empty] | 3
S_24 | Blaenau Gwent County Borough Council | General Government | Local authority |  | 3 | [29 empty] | 2 |  |  | 2
S_25 | BlueTech Research | Education | Higher Education |  |  |  |  | 2
S_26 | Boliden Tara Mines | Industry | Mining | [35 empty] | 2
S_27 | Bon Secours Hospital Galway | Health care | Hospital | [10 empty] | 2
S_28 | Borrmont GWS | Utility | Water provider | [7 empty] | 2
S_29 | BPD Limited | Industry | Plumbing and heating |  |  |  |  | 2
S_30 | Brandon House Hotel | Hospitality | Brandon House Hotel | [15 empty] | 2
S_31 | Bring It To The Lab | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_32 | Bundoran Waterworld CLG | Sport Facilities | Leisure Centre | [9 empty] | 3
S_33 | Business and Industry Committee, RDS | No-profit institution | Charity | 3
S_34 | Byw'n Iach | Sport Facilities | Leisure Centre | [9 empty] | 3 | [32 empty] | 2
S_36 | Calon Tysul | Sport Facilities | Leisure Centre | [9 empty] | 3 | [31 empty] | 4
S_37 | Cardiff University | Education | Higher Education |  | 3 | 3
S_38 | Carlow County Council | General Government | Local authority |  |  |  | 2
S_39 | Carlow IT | Education | Higher Education | 3
S_40 | Caulmert Ltd | Professional, administration and support services | Consultancy |  |  | 3
S_41 | Centre for Alternative Technology Wales | Education | Higher Education | [6 empty] | 3
S_42 | Club Vitae Oranmore, Galway | Sport Facilities | Leisure Centre | [9 empty] | 3
S_43 | Codema | No-profit institution | Agency | [11 empty] | 2
S_44 | Colman Hession and Associates Engineers | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_45 | Commission for Energy Regulation | General Government | Government agency | 3
S_46 | Commission for Regulation of Utilities | General Government | Government agency |  | 3 |  |  | 2
S_47 | Consumer Council for Water | General Government | Government agency |  | 3
S_48 | Coolagh Caherleske GWS | Utility | Water provider | [51 empty] | 2
S_49 | Cooleeney Cheese | Agriculture | Farm
S_50 | Coolmore Park GWS | Utility | Water provider
S_51 | Co-Operative Housing Ireland (CHI) | General Government | Approved Housing Body | [8 empty] | 3
S_52 | Coral Leisure killarney | Sport Facilities | Leisure Centre | [9 empty] | 3
S_53 | Coral Leisure Ltd | Sport Facilities | Leisure Centre | [9 empty] | 3 | 2 | 2 | 2 | 2
S_54 | Corwn Leisure Centre | Sport Facilities | Leisure Centre | [40 empty] | 3
S_55 | Cosyn Cymru | Industry | Dairy | [10 empty] | 2
S_56 | Cullahill/Seskin GWS | Utility | Water provider | [7 empty] | 2
S_57 | Cully Automation | Professional, administration and support services | Consultancy |  |  |  | 2 | 2
S_58 | Cwrw Lyn Brewery | Industry | Beverage
S_59 | Cyfoeth Naturiol Cymru / Natural Resources Wales | General Government | Government agency |  | 3 | 3 |  |  |  | 3 | [6 empty] | 2 | [34 empty] | 2
S_60 | Cyngor Gwynedd Council | General Government | Local authority |  | 3 | [7 empty] | 3 | [32 empty] | 2
S_61 | Dairygold | Industry | Dairy | [36 empty] | 2
S_62 | DCU | Education | Higher Education |  |  |  | 2 | 2
S_63 | Dean of Research TCD | Education | Higher Education | 3
S_64 | Denbighshire County Council | General Government | Local authority | [40 empty] | 2 |  | 2
S_65 | Denbighshire Leisure | Sport Facilities | Leisure Centre | [40 empty] | 2 |  | 2
S_66 | Department of Housing, Planning, Community & Local Government | General Government | Government department | 3 |  |  | 2 |  | 3 | [10 empty] | 1
S_67 | Detectronic Ltd | Professional, administration and support services | Consultancy |  | 3
S_68 | Donal Mc Kenna | Professional, administration and support services | Consultancy | [11 empty] | 2 | 2
S_69 | Driftwood Experience Ltd | Hospitality | Café | [12 empty] | 2
S_70 | Druids Glen Hotel | Hospitality | Hotel | [49 empty] | 2
S_71 | Dublin City Council | General Government | Local authority |  |  |  |  | 2 | [28 empty] | 2
S_72 | Dulas Ltd | Professional, administration and support services | Consultancy | 3 | 3 |  |  |  |  | 3
S_73 | Dunne Technical Services | Professional, administration and support services | Consultancy | [5 empty] | 3
S_74 | Dwr Cymru Welsh Water (DCWW) | Utility | Water provider | 3 | 3 | 3 |  | 2 |  | 3 | [7 empty] | 2 | [17 empty] | 2 | [17 empty] | 1
S_76 | Egnida | Professional, administration and support services | Consultancy |  |  | 3
S_77 | EIP on Water / Baur Technology | European body | Agency | 3
S_78 | Energy Elephant | Professional, administration and support services |  | 3
S_79 | Energy Saving Trust | Professional, administration and support services | Consultancy | 3
S_80 | Engineers Ireland | No-profit institution | Professional Association |  |  |  |  | 2
S_81 | ENICA Ltd | Professional, administration and support services | Technology |  |  | 3 | [16 empty] | 4
S_82 | Epro Advance Technology Ltd | Utility | Energy provider | [13 empty] | 2
S_83 | EPS Group | Professional, administration and support services |  | 3 |  |  |  | 2 | 3 |  |  |  |  | 2 |  |  | 2 |  |  | 4 | [13 empty] | 2
S_84 | Feedzai | Financial and insurance activities | Risk management | [11 empty] | 2
S_85 | Fermanagh Omagh District Council | General Government | Local authority | [9 empty] | 3
S_86 | Finance, Bangor University | Education | Higher Education | 3
S_87 | Fingleton White | Professional, administration and support services | Consultancy | [10 empty] | 2
S_88 | Flintshire County Council | General Government | Local authority | [10 empty] | 2
S_89 | Food Technology Centre | Professional, administration and support services | Consultancy |  |  | 3
S_90 | Forta Pro | Constrution | Building company | [10 empty] | 2
S_91 | Forterra | Constrution | Building materials |  |  | 3
S_92 | Gas Networks | Utility | Energy provider |  |  |  |  | 2
S_93 | General Public | Households | General public |  |  |  |  | 2 |  | 3 | [7 empty] | 2
S_95 | GIP Campus | Education | Higher Education | [11 empty] | 2 | 2
S_96 | Glan Agua | Professional, administration and support services | Consultancy | [37 empty] | 2
S_97 | GLL | Sport Facilities | Leisure Centre | [9 empty] | 3
S_98 | Glynn St. Mullins Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2
S_99 | Green Connection | Professional, administration and support services | Consultancy | [13 empty] | 2
S_100 | H2 Ozone | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_101 | HC Financial Training | Financial and insurance activities | Consultancy | 3
S_102 | Heath Group Water Scheme | Utility | Water provider |  |  |  | 2 | 2
S_103 | Higher Education Authority (HEA) | General Government | Statuatory body | 3
S_104 | Hinds book shop | Retailing | Book shop |  |  |  |  | 2
S_105 | Hogg Enterprises | Agriculture | Support service | [5 empty] | 3
S_106 | HSE | General Government | Agency | [10 empty] | 2 | 2 | 2
S_107 | IBERS | Education | Higher Education |  |  | 3
S_108 | Imperial Hotel Galway | Hospitality | Hotel | [15 empty] | 2
S_109 | Imperial Hotel Llandundo | Hospitality | Hotel | [38 empty] | 2
S_110 | Innogy Renewables uk | Industry | Manufacturing |  |  | 3
S_111 | International Hotel Killarney | Hospitality | Hotel | [15 empty] | 2
S_112 | Interreg Ireland-Wales Programme | General Government | Agency | 3
S_113 | Ireland-Wales PSC | General Government | Agency | 3
S_114 | Irish Rail | Transport | Company |  |  |  |  | 2
S_115 | Irish Water | Utility | Water provider | 3 |  |  |  | 2 | [8 empty] | 2 | 2
S_116 | JLA Hydro | Professional, administration and support services | Consultancy | [10 empty] | 2 | 2 | 2 | 2
S_117 | Kerry County Council | General Government | Local authority | 3 | [8 empty] | 3
S_118 | Kilanerin Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2 | [21 empty] | 2
S_119 | Kilcredan GWS | Utility | Water provider | [51 empty] | 2
S_120 | Kildare County Council | General Government | Local authority | [5 empty] | 3
S_121 | Kilkenny County Council | General Government | Local authority |  |  |  | 2
S_122 | Killally Ballinrush GWS | Utility | Water provider | [51 empty] | 2
S_123 | Kilriffith Kilmore GWS | Utility | Water provider | [51 empty] | 2
S_124 | Kings Mill Kilkenny | Entertainment | Heritage site | [52 empty] | 2
S_125 | Langton House Hotel | Hospitality | Hotel | [15 empty] | 2
S_126 | Laois County Council | General Government | Local authority | [5 empty] | 3
S_127 | Lovegrove EBS Ltd | Professional, administration and support services | Consultancy |  |  | 3 | [6 empty] | 3 | 2 |  | 2
S_128 | Mark Eire BV | Professional, administration and support services | Technology | [9 empty] | 3
S_129 | Martin J Hughes Glas Cymru | Utility | Water provider | [11 empty] | 2 | [35 empty] | 2
S_130 | Mayo County Council | General Government | Local authority | [9 empty] | 3
S_131 | Mbarara University of Science and Technology | Education | Higher Education | [12 empty] | 2
S_132 | Menai Science Park | Professional, administration and support services | Business support | [43 empty] | 3
S_133 | Moyne GWS | Utility | Water provider | [51 empty] | 1
S_134 | Mullaun Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2
S_135 | Narraghmore Group Water Scheme | Utility | Water provider |  |  |  | 2
S_136 | National Council of Ireland | General Government | Agency |  |  |  |  | 2
S_137 | National Federation of Group Water Schemes (NFGWS) | Utility | Water provider | 3 | 3 |  | 2 | 2 | 3 |  | 2 |  |  | 2 | [5 empty] | 3 |  |  |  |  | 3 | 3
S_138 | National Research Network - Low Carbon Energy & Environment | Education | Higher Education | 3
S_139 | National Trust (NT) | No-profit institution | Charity | [6 empty] | 3 | [12 empty] | 3 | 3 | [26 empty] | 3 | 2 | 2
S_140 | National Trust Wales | No-profit institution | Charity | 3 | 3 | [17 empty] | 4 | 4 | [26 empty] | 3 | 2 | 2
S_141 | Nenagh Swimming Pool | Sport Facilities | Leisure Centre | [49 empty] | 2
S_142 | Neville Park Hotels | Hospitality | Hotel | [15 empty] | 2
S_144 | Nicholas O'Dwyer Ltd | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_145 | Noel Lawlor Consulting Engineers | Professional, administration and support services | Consultancy | [49 empty] | 2
S_146 | Nova Centre Prestatyn | Sport Facilities | Leisure Centre | [40 empty] | 3 |  | 4
S_147 | NTC - Nexus Technologies Concepts | Professional, administration and support services | Consultancy | [10 empty] | 2 |  |  | 2
S_148 | NUI Galway | Education | Higher Education |  | 3
S_149 | Ogwen Hydro | Professional, administration and support services | Consultancy | [56 empty] | 2
S_150 | Operational Support Services Limited | Professional, administration and support services | Consultancy |  | 3
S_151 | OzoneTech | Professional, administration and support services | Technology |  |  |  |  | 2
S_152 | Pant Glas Padog Conwy | Agriculture | Farm | [6 empty] | 3
S_153 | Parkwood Leisure | Sport Facilities | Leisure Centre | [9 empty] | 3
S_154 | Patrickswell GWS | Utility | Water provider | [51 empty] | 1
S_155 | PepsiCo Ireland | Industry | Beverage | [49 empty] | 2
S_156 | Pool Sentry | Sport Facilities | Leisure Centre | [9 empty] | 3 | [32 empty] | 4
S_157 | Portarlington Leisure Centre | Sport Facilities | Leisure Centre | [9 empty] | 3
S_158 | Portmagee Whiskey distillery | Industry | Beverage
S_159 | Q -Blue BV | Industry | Manufacturing |  |  |  |  | 2 | [10 empty] | 2
S_160 | Rain Surfer | Professional, administration and support services | Technology |  |  |  |  | 3
S_162 | Rhyl Leisure Centre | Sport Facilities | Leisure Centre | [40 empty] | 3 |  | 4
S_163 | Roscommon City Council | General Government | Local authority |  |  |  | 2
S_164 | RPS Group | Professional, administration and support services | Consultancy | 3 |  |  |  | 2 | [5 empty] | 2
S_165 | Ruthin Leisure Centre | Sport Facilities | Leisure Centre | [40 empty] | 3
S_166 | Ryan Hanley Ltd | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_167 | Saudi Aramco | Industry | Oil | [10 empty] | 2
S_168 | SC2 leisure centre | Sport Facilities | Leisure Centre | [40 empty] | 3 |  | 4
S_169 | Shannon Swimming & Leisure Centre | Sport Facilities | Leisure Centre | [9 empty] | 3
S_170 | shri Ram Rayons | Industry | Manufacturing | [13 empty] | 2
S_171 | Siemens | Industry | Technology |  |  |  |  | 2
S_172 | Southern Regional Assembly | General Government | Agency |  |  |  | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 |  | 2 | [32 empty] | 2
S_174 | Sustainability Lab | Education | Higher Education | [6 empty] | 3
S_175 | Sustainable Energy Authority of Ireland | General Government | Agency |  | 3
S_176 | Sustainable Travel Ireland | Professional, administration and support services | Tourism | [15 empty] | 2
S_177 | Talbot Hotel Group | Hospitality | Hotel | [15 empty] | 2
S_178 | Talbot Hotel Stillorgan | Hospitality | Hotel | [49 empty] | 2
S_179 | Tan y Lan Fach | Hospitality | Accommodation | [10 empty] | 2 | 2 | 2 | 2
S_180 | TCFG | No-profit institution | Community | [46 empty] | 2
S_181 | Technological University Dublin | Education | Higher Education | [10 empty] | 2 | 2 |  | 2
S_182 | Temple Gate Hotel | Hospitality | Hotel | [15 empty] | 2
S_183 | The Brown's | Hospitality | Hotel |  |  | 3
S_184 | The Brunner CBS | Education | Higher Education | [53 empty] | 2
S_185 | The Clanard Court Hotel | Hospitality | Hotel | [15 empty] | 2
S_186 | The Grand Hotel Dublin | Hospitality | Hotel | [15 empty] | 2
S_187 | The Green Valleys CIC | No-profit institution | Community | [10 empty] | 2
S_188 | The Rediscovery Centre | No-profit institution | Charity | [12 empty] | 2 | [26 empty] | 2
S_189 | The Savoy Hotel | Hospitality | Hotel | [15 empty] | 2
S_190 | The Start | Hospitality | Accommodation |  |  | 3
S_191 | The University of the West of England | Education | Higher Education |  | 3
S_192 | The Watershed | Sport Facilities | Leisure Centre | [9 empty] | 3
S_193 | The Watershed Kilkenny | Sport Facilities | Leisure Centre | [9 empty] | 3
S_194 | Tipperary County Council | General Government | Local authority |  |  |  | 2 | 2 | 3 |  |  |  |  | 2
S_196 | UCD | Education | Higher Education |  |  |  |  | 2
S_197 | UMNG | Education | Higher Education | [13 empty] | 2
S_198 | Universidad de Valencia | Education | Higher Education | [10 empty] | 2 | 2 |  | 2
S_199 | Universitat Jaume I | Education | Higher Education |  |  |  |  | 2
S_200 | University of Cordoba | Education | Higher Education | 3 | 3
S_201 | University of the Philippines | Education | Higher Education | [12 empty] | 2
S_202 | VEOLIA Environmental Services Technical Solutions Limited | Professional, administration and support services | Consultancy | 3
S_203 | Verde Environmental Consulting | Professional, administration and support services | Consultancy | [10 empty] | 2
S_204 | volunteer | Households | General public | [14 empty] | 2
S_205 | Walterstown GWS | Utility | Water provider | [51 empty] | 2
S_206 | Watef Network | No-profit institution | Network | 3 | 3
S_207 | Water CoLab | Professional, administration and support services | Business support |  |  |  |  | 2
S_208 | Water Loss Research & Analysis Ltd | Professional, administration and support services | Consultancy |  | 3
S_209 | Water Turbines PLC | Constrution | Infrastructure | 3 | 3
S_210 | Waterford County Council | General Government | Local authority |  |  |  | 2
S_211 | Waterways Ireland | General Government | Agency | [10 empty] | 2
S_212 | Waterwise | No-profit institution | Advocacy | 3
S_213 | Welsh Assembly | General Government | Government department |  | 3
S_214 | Welsh Government | General Government | Government department |  |  | 3 | [7 empty] | 2 | 2 | 2 | 2 | 2 | [33 empty] | 2
S_215 | WEW Consulting | Professional, administration and support services | Consultancy | [5 empty] | 3
S_216 | Wexford City Council | General Government | Local authority |  |  |  | 2
S_217 | Wexford County Council | General Government | Local authority | [5 empty] | 3 | [10 empty] | 1
S_218 | Wicklow County Council | General Government | Local authority |  |  |  | 2 |  | 3
S_219 | Wicklow Uplands council | No-profit institution | Voluntary organisation | [10 empty] | 2 |  | 2
S_220 | Woodford Dolmen Hotel | Hospitality | Hotel | [15 empty] | 2
S_221 | Yangzhou university | Education | Higher Education | [14 empty] | 2
S_222 | Ymgynghoriaeth Gwynedd Consultancy | Professional, administration and support services | Consultancy | [55 empty] | 2
S_223 | Ynni Llyn - community energy scheme | No-profit institution | Community | [6 empty] | 3
S_224 | Ynni Ogwen | Utility | Energy provider | [6 empty] | 3
S_225 | Ynys Resources Ltd | Professional, administration and support services | Consultancy |  | 3
S_226 | Arbikie Distillery | Industry | Beverage | [54 empty] | 4
S_161 | Rathnure National School | Education | Primary Education | [21 empty] | 3 | 3
S_35 | Caim National School | Education | Primary Education | [21 empty] | 2 | 2
S_173 | St Joseph Donard National School | Education | Primary Education | [21 empty] | 2 | 2
S_13 | Ballinabranna National School | Education | Primary Education | [21 empty] | 3
S_143 | Newpark Comprehensive School | Education | Secondary education | [23 empty] | 4
S_75 | ECOUNESCO | No-profit institution | Charity | [24 empty] | 3
S_11 | Ballacolla Group Water Scheme | Utility | Water provider | [26 empty] | 2
S_94 | Gibneys of Malahide | Hospitality | Pub | [44 empty] | 3
S_227 | Mountain Studios | Utility | Water provider | [47 empty] | 2
S_228 | The Royal Victoria Hotel | Utility | Water provider | [47 empty] | 2
S_229 | Geosmart Decision | Utility | Water provider | [48 empty] | 2
S_230 | University of Bath | Utility | Water provider | [48 empty] | 2
S_231 | University of Exeter | Utility | Water provider | [48 empty] | 2
S_232 | Pforzheim University (Germany) | Utility | Water provider | [48 empty] | 2
S_233 | Northumbrian Water | Utility | Water provider | [48 empty] | 2
S_18 | Bangor University St Mary's Student Accommodation | Hospitality | Bangor University St Mary's Student Accommodation | [45 empty] | 2
S_234 | Arfon Leisure Centre | Sport Facilities | Leisure Centre | [42 empty] | 4
S_235 | Bangor Leisure Centre | Sport Facilities | Leisure Centre | [42 empty] | 4
S_236 | Glaslyn Leisure Centre | Sport Facilities | Leisure Centre | [42 empty] | 4

## links
ID | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [24 empty] | 1
2 | 1 |  | 1 |  | 1 | 1 |  | 1 | [24 empty] | 1
3 | 1 | 1 | [30 empty] | 1
4 | 1 | [22 empty] | 1 |  |  | 1 | 1 |  | 1 |  |  | 1 | [7 empty] | 1 | [7 empty] | 1
5 | 1 | 1 | [30 empty] | 1
6 | 1 | 1 |  |  |  |  | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | [7 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | [9 empty] | 1 |  |  | 1
7 | 1 |  |  |  |  | 1 |  | 1 | [24 empty] | 1
8 | 1 | 1 |  | 1 |  | 1 | [26 empty] | 1
9 | [9 empty] | 1 | [22 empty] | 1
10 | [8 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [16 empty] | 1 | [15 empty] | 1 | [41 empty] | 1
11 | [14 empty] | 1 | [17 empty] | 1
12 | [9 empty] | 1 |  |  | 1 | 1 | 1 | 1 | [16 empty] | 1 | [8 empty] | 1 |  |  |  |  | 1 |  | 1 |  | 1
13 | [15 empty] | 1 | [16 empty] | 1
14 | [5 empty] | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | [7 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  | 1
15 | [11 empty] | 1 |  | 1 |  | 1 | [16 empty] | 1 | [15 empty] | 1
16 | [9 empty] | 1 |  | 1 | 1 | 1 | 1 | [17 empty] | 1 | [15 empty] | 1
17 | [32 empty] | 1 | [62 empty] | 1
18 | [32 empty] | 1 | [32 empty] | 1
20 | [5 empty] | 1 | [7 empty] | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  |  | 1
21 | 1 | 1 | [16 empty] | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
22 |  | 1 | [16 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
23 |  | 1 | [16 empty] | 1 | 1 | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1
24 |  | 1 | [16 empty] | 1 | 1 | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1
25 | 1 |  |  | 1 |  | 1 | [17 empty] | 1 |  |  | 1 |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  |  | 1
26 | 1 | 1 | [9 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [45 empty] | 1
27 |  | 1 | [5 empty] | 1 | [16 empty] | 1 |  | 1 |  |  | 1 |  |  | 1
28 | [24 empty] | 1 | 1 |  | 1 |  | 1 |  |  | 1 | [16 empty] | 1 | 1
29 | [18 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | [56 empty] | 1
30 |  |  |  | 1 |  | 1 | [7 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 | [6 empty] | 1
31 | 1 | [6 empty] | 1 | [16 empty] | 1 | 1 | 1 | [5 empty] | 1
32 | [11 empty] | 1 | 1 | [11 empty] | 1 |  |  | 1 |  |  |  | 1 | 1 | [56 empty] | 1
33 | [11 empty] | 1 | 1 | [11 empty] | 1 |  |  | 1 |  |  | 1 |  | 1 | [56 empty] | 1
34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
35 | [32 empty] | 1 | [15 empty] | 1
36 | [27 empty] | 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1
37 |  |  |  | 1 |  | 1 | [7 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1
38 | [27 empty] | 1 |  |  |  |  | 1 |  |  | 1 | 1
39 | [27 empty] | 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1
40 | [27 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1
41 | [27 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
42 |  |  |  | 1 | [19 empty] | 1 |  |  | 1 | [5 empty] | 1 | 1 | [14 empty] | 1
43 | [5 empty] | 1 | [5 empty] | 1 | 1 | 1 | [9 empty] | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | [9 empty] | 1 | 1 | 1 | 1 |  | 1 | 1
44 | [32 empty] | 1 | [14 empty] | 1
45 | [8 empty] | 1 |  | 1 | 1 | [12 empty] | 1 | [7 empty] | 1 | [11 empty] | 1
46 | [32 empty] | 1 | [10 empty] | 1
47 | [5 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 | 1 | [7 empty] | 1
48 | [11 empty] | 1 | 1 | [19 empty] | 1 | [11 empty] | 1 | [13 empty] | 1 | [24 empty] | 1 | [6 empty] | 1
49 | [13 empty] | 1 | [18 empty] | 1 | [8 empty] | 1 | 1
50 | [13 empty] | 1 | 1 | 1 | [16 empty] | 1
51 | 1 | 1 | [24 empty] | 1 | [5 empty] | 1 | [18 empty] | 1 | 1 | 1
52 | [26 empty] | 1 | 1 |  |  |  |  | 1 | [18 empty] | 1 | 1 | 1
53 | [26 empty] | 1 | [5 empty] | 1 | [17 empty] | 1 |  | 1 | 1
54 | [26 empty] | 1 | [5 empty] | 1 | [17 empty] | 1 | 1 |  | 1
55 | [26 empty] | 1 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 1 | 1
56 | [27 empty] | 1 |  |  |  |  | 1 | [22 empty] | 1 |  | 1 | [6 empty] | 1
57 | [27 empty] | 1 |  |  |  |  | 1 | [21 empty] | 1 |  | 1 | [6 empty] | 1
58 | [26 empty] | 1 | [5 empty] | 1 | [22 empty] | 1
59 | [26 empty] | 1 | [5 empty] | 1 | [21 empty] | 1 | [9 empty] | 1
60 | [8 empty] | 1 | 1 | 1 | [21 empty] | 1
61 | [32 empty] | 1
62 | [32 empty] | 1
63 | [32 empty] | 1
64 | 1 | 1 | [22 empty] | 1 |  | 1 | [5 empty] | 1
65 | [32 empty] | 1
66 | [32 empty] | 1 | [24 empty] | 1 | [36 empty] | 1
67 | [17 empty] | 1 | [14 empty] | 1 | [57 empty] | 1 |  |  |  |  | 1
68 | [32 empty] | 1 | [34 empty] | 1 | 1 | 1
69 | [32 empty] | 1 | [33 empty] | 1
70 | [32 empty] | 1 | [33 empty] | 1 | 1 |  | 1
71 | [32 empty] | 1 | [33 empty] | 1 | 1 | 1
72 | 1 | [31 empty] | 1 | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
73 | 1 | [31 empty] | 1 | [37 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
74 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
75 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
76 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
77 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
78 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
79 | 1 | 1 | [30 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
80 | 1 | [23 empty] | 1 | [7 empty] | 1 | [16 empty] | 1 | 1 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
81 | [32 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
82 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | [10 empty] | 1 | 1 |  |  |  | 1
83 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1 |  |  |  | 1
84 | [32 empty] | 1
85 | [32 empty] | 1
86 | [32 empty] | 1
87 | [32 empty] | 1
88 | [32 empty] | 1
89 | [25 empty] | 1 |  |  |  | 1 | 1 | 1 | 1
90 | [25 empty] | 1 |  |  |  | 1 | 1 | 1 | 1 | [56 empty] | 1
91 | [32 empty] | 1 | [55 empty] | 1
92 | [9 empty] | 1 |  | 1 | [20 empty] | 1
93 | [32 empty] | 1
94 | 1 | [31 empty] | 1
95 | 1 | [31 empty] | 1
96 | [32 empty] | 1
97 | [32 empty] | 1
98 | [32 empty] | 1 | [52 empty] | y | [10 empty] | 1
99 | 1 | [31 empty] | 1 | [59 empty] | 1 | 1