## Activities
actividad | WP | Start Month | End Month | Activity description | category | Single/Inter/Trans-disciplinary
1 | 1 | 1 | 33 | Design, procurement, installation supervision, commissioning of a 3.3 kW hydro pilot plant at the Blackstairs Water Treatment Plant in Co. Wexford (Ireland) | Installation/Demo site | Transdisciplinary
2 | 1 | 1 | 39 | Design, procurement, installation supervision, commissioning of a 3.6 kW hydro pilot plant on a site owned by National Trust Wales (UK) | Installation/Demo site | Transdisciplinary
3 | 1 | 1 | 26 | Journal publication | Publication | Single Discipline
4 | 1 | 57 | 64 | The webinar is a place-based 45 minute on-line workshop for primary school pupils in 4th to 6th class. Topics: it covers the natural and man made water cycle; the Blackstairs GWS scheme details; the MHP system details. The workshop is interactive and engaging with a number of hands-on activities, including a group activity to design and plan for climate action in their schools or communities. | Event | Transdisciplinary
5 | 1 | 1 | 33 | Journal publication | Publication | Single Discipline
6 | 1 | 54 | 54 | A 1 hour long webinar about Low-cost and modular hydro turbines: opportunity, design and results from pilot installations .Since 2011 the research team Trinity College Dublin has been working on a novel type of low-cost and modular water turbine, consisting of using regular water pumps in reverse as turbines. The webinar will introduce the technology and provide an overview of the locations where it could be beneficial. Also, the results from the various installed pilot plants operating since 2019 will be presented. | Event | Interdisciplinary
7 | 1 | 38 | 62 | Journal publication | Publication
8 | 1 | 33 | 78 | This part of the project is related to the ongoing monitoring and maintainance of the two micro-hydropower demonstration sites | Installation/Demo site
9 | 2 | 1 | 29 | Journal publication to present the results of spatial and temporal influences in the performance of wastewater heat recovery systems at residence scale in Ireland | Publication
10 | 2 | 1 | 35 | Journal publication assessing the impact of introducing direct drain water heat recovery systems in commercial kitchens in the UK, based on a commercially available heat exchangers. | Publication
11 | 2 | 1 | 40 | This study illustrates a method to include both the spatial and temporal aspects in the assessment of the operation and feasibility of an effluent heat recovery system at a WWTP. This leads to a more detailed and comprehensive prediction of the actual recovered heat, and thus allows for a more precise prediction of the feasibility of such projects. The application on a case study in Ireland indicated the general practicability of the suggested method as well as the promising potential of wastewater heat recovery, and the role it can play to reach renewable energy and greenhouse gas reduction targets. | Publication
12 | 2 | 1 | 42 | This project concerns the design, planning and installation of the DWHR system at Penrhyn Castle in N Wales | Installation/Demo site | Transdisciplinary
13 | 2 | 42 | 78 | Data recorded at Penrhyn Castle is monitored to assess how much heat is recovered from the system installed in the café | Installation/Demo site | Interdisciplinary
14 | 4 | 55 | 55 | Webinar to introduce heat recovery toolkit to public. | Event | Interdisciplinary
15 | 4 | 31 | 55 | Development of a heat recovery toolkit for commercial kitchen owners (pubs, restaurants, cafes, canteens etc.) to get an estimate on their individual heat recovery potential from drain water, environmental and cost savings (or trade-offs); to support and facilitate uptake of heat recovery from drain water in commercial kitchens. | Tool | Interdisciplinary
16 | 4 | 23 | 47 | Exploring the environmental footprint of heat recovery installations for drain water heat recovery from commercial kitchens (Penrhyn castle and in general, kitchens in the UK). | Publication | Interdisciplinary
17 | 4 | 35 | 64 | Publication: Life Cycle Assessment of whisky (Scotch Single Malt whisky) production and by-product use. Focus on water footprint and carbon emissions. | Publication | Single Discipline
18 | 4 | 31 | 74 | Exploring the environmental and financial benefits (and trade-offs) of recovering heat in a distillery from process and waste flows. Focus on the impact categories climate change (GHG emissions) and water scarcity impacts. | Publication | Interdisciplinary
20 | 7 | 62 | 62 | A webinar chaired by Sopan Patil, with Richard Dallison as speaker, presenting the results of WP7 work on the impacts of future climate change on water resources in Wales, and the implications for hydropower production. Results for Wales were put in the context of the wider UK, and for other water abstractors. | Event | Transdisciplinary
21 | 7 | 53 | 78 | Study investigating how future worst-case scenario climate change will impact on the timing and quantity of streamflow at 585 catchments across the UK and Ireland, and the knock-on implications of such changes for water abstraction at 531 hydropower locations in 178 catchments in England, Wales, Scotland, Ireland & Northern Ireland. | Project | Single Discipline
22 | 7 | 1 | 18 | Study investigating the historical trends in mean and extreme streamflow, temperatures, and precipitation, in five catchments in Wales. | Project | Single Discipline
23 | 7 | 19 | 52 | Study investigating future trends in mean and extreme streamflow, as well as water quality, for five catchments in Wales, in worst-case scenario future climate change. | Project | Single Discipline
24 | 7 | 18 | 47 | Study investigating the impacts of future climate change induced streamflow alterations on water available for public water supply and hydropower, using two catchments in Wales as case studies. | Project | Single Discipline
25 | 8 | 57 | 64 | The webinar is place-based 45 minute on-line workshop for primary school pupils in 4th to 6th class in school served by BGWS. Topics: it covers the natural and man made water cycle; the Blackstairs GWS scheme details; the MHP system details. The workshop is interactive and engaging with a number of hands-on activities, including a group activity to design and plan for climate action in their schools or communities. | Event | Transdisciplinary
26 | 8 | 1 | 78 | Four demonstration sites to showcase the techological solutions were planned and implemented as part of Dwr Uisce with the aim of bringing outside of the lab the technology and to demonstrate in practice how they work and how they can benefit the users. Each of the installation at the different demonstration sites underwent a process of lab testing, prototyping, implementation, feedback from other stakeholders involved. The four fall in two main categories: micro-hydropower installations and heat recovery systems. | Installation/Demo site | Transdisciplinary
27 | 8 | 39 | 39 | Official opening of the demonstration site in Tŷ Mawr Wybrnant, Wales (UK) on 21/11/19. The event was about demonstrating a novel technology such as the application of a pump-as-turbine to produce energy from a small stream running along the land, property of the National Trust Wales. The energy produced is used within Ty Mwr to power a dehumidifying system that preserves the first Welsh-translated bible from beign damaged by the dampness. Associated information board remains as a legacy of the project communicting key features to visitors. | Event | Transdisciplinary
28 | 8 | 1 | 78 | The SSC and Water-Energy Network aim to facilitate dissemination of information and technology, and collaboration within the network of participating enterprises. The smart specialisation cluster comprises key actors in the sector in Ireland and Wales, supplemented by outside expertise where appropriate. In the context of the Dŵr Uisce project, the smart specialisation cluster can be seen as a learning network of enterprises. | Project | Transdisciplinary
29 | 8 | 1 | 78 | Tools for dissemination and for translating research into ordinary speak. | Communication | Interdisciplinary
30 | 8 | 54 | 78 | A series of free sustainability webinars to present the findings, challenges and practical solutions to improving energy efficiency in the water sector. | Event | Interdisciplinary
31 | 8 | 33 | 33 | Official opening of the demonstration site in Blackstairs (Co. Wexford, Ireland) on 02/05/19. The event was about demonstrating a novel technology such as the application of a pump-as-turbine to recover energy in a water supply network managed by a Group water Scheme. The event was used as an intervention to elict knowledge sharing, feedback and dissemination of the idea, in order to accelerate adoption of the technological solution by other suitable water network operators. Associated information board remains as a legacy of the project communicting key features to visitors. | Event | Transdisciplinary
32 | 8 | 62 | 78 | We are planning to deliver a short training to staff from NTW to raise awarenss of the installed heat recovery system | Communication
33 | 8 | 62 | 78 | We developed information boards to share the details of the DWHR system as well as raising awareness of the climate action potential of the system | Communication
34 | 8 | 1 | 52 | The project aims to improve the long-term sustainability of water supply, treatment and end-use in Ireland and Wales. This improvement is to be achieved through the development of new innovative technology platforms, undertaking economic and environmental impact assessments, and developing policy and best practice guidelines to facilitate the implementation of integrated low-carbon and smart energy solutions. The scope of Dŵr Uisce covers three themes: Technology Platforms; Policy Support and Guidance; and, Dissemination and Collaboration. | Publication | Interdisciplinary
35 | 3 | 63 | 63 | In person workshop to present the software EPANET to members of the Group Water Schemes and to illustrate the features, possibilities and some potential applications to manage their networks | Event
36 | 6 | 30 | 42 | Assessing the water-energy efficiency of wet leisure centre stock of a local authority in North Wales. | Project | Interdisciplinary
37 | 6 | 54 | 54 | A panel discussion of experts working in different areas of leisure centre design, development, operation, and management that discussed the potential for existing leisure centres to adopt heat recovery as a means of emissions reductions and costs savings, particularly with respect to Covid-19 and net-zero targets and ambitions. | Event | Transdisciplinary
38 | 6 | 43 | 78 | Assessing and quantifying the whole building potential (NZEB) of a community-run rural leisure centre in mid-Wales: case study. | Project | Interdisciplinary
39 | 6 | 43 | 70 | Monitoring, assessment and quantification of the water-energy use efficiency and management on resource use, carbon footprint, and water quality of existing swimming pools in North Wales. | Project | Transdisciplinary
40 | 6 | 43 | 49 | Assessing the water-energy efficiency potential of office water use in a new-build science park on Anglesey, Wales. | Project | Interdisciplinary
41 | 6 | 55 | 78 | Assessing and quantifying the water-energy efficiency of a historic pub/ restaurant in Dublin. Case study for heat recovery potential of commercial pub kitchen. | Project | Interdisciplinary
42 | 8 | 67 | 78 | The workshop, based on the content and activities developed for BGWS, has been adapted to be used by other GWSs in collaboration with NFGWS | Event | Transdisciplinary
43 | 2 | 55 | 55 | 1-hour long webinar to present the concept and applications of DWHR | Event | Transdisciplinary
44 | 2 | 61 | 78 | Development of thermal recovery unit for enhanced heat recaptre from the kitchens wastewater. Furthermore, analyse the impact of heat recovery on grease trap removal efficiency. In near future, new heat exchanger material design in our portfolio to explore with an objective to develop cost-effective and thermally competent system design. | Technology | Single Discipline
45 | 2 | 21 | 78 | This project concerns the design, planning and installation of the DWHR system at ABP in Tipperary, Ireland | Installation/Demo site | Transdisciplinary
46 | 2 | 41 | 78 | Data recorded at ABP is monitored to assess how much heat is recovered from the system installed in meat factory | Installation/Demo site | Transdisciplinary
47 | 5 | 56 | 56 | 1- hour long webinar to present to the general public and SSC memmebrs the output of the benchmarking work | Event | Interdisciplinary
48 | 2 | 65 | 78 | The student accommodation has been monitored using tiny tags to assess the heat recovery potential | Project | Transdisciplinary
49 | 2 | 64 | 64 | The grease trap has been nmonitored for three weeks in December 2021 to evaluate the temperature of the drainwater leaving the kitchen of the on-site café to assess the heat recovery potential | Project | Transdisciplinary
50 | 4 | 68 | 68 | A 1 hour long webinar targeted to the hospitality sector to present DWHR from commercial kitchens in theory and practice by illustrating the demo site at Penrhyn Castle.Also the Heat recovery Tool was presented and participants were given the time to explore the tool and test the feasibility of applying the system in their kitchens using their data. | Event | Interdisciplinary
51 | 8 | 2 | 2 | The kick-off event took place in 2016 and included presentations by principal investigators from Trinity College and Bangor University; a structured group discussion in the morning. In the afternoon, two 10-mins presentations were delivered by two demonstrators Welsh Water and National Trust Wales. Those were followed by a breakout session which included all participants. Three pre-formed goups were assigned as follows: 1 WW representative and 2 NTW representatives. DU team mebers placed themselves strategically according to individual project responsibility and interests among the three groups to prompt, observe and note the questioning. At the end each participant was given a one-page questionnaire in order to record specific details about each of them in terms of personal and organizational motivation, contribution, interest, and expectations. | Event | Transdisciplinary
52 | 8 | 14 | 14 | The first annual Dwr Uisce Conference was hosted by Bangor University in Wales. The theme of the conference aimed to address the challenges we face in relation to water and energy demands in our region. The event included guest speakers on technical, social and governance perspectives on the importance of valuing our water and energy resources, and discussed how we can ensure water and energy security in the future. There was also an opportunity for conference participants to give their own 2-minute perspective on an energy efficiency water sector. | Event | Transdisciplinary
53 | 8 | 18 | 18 | This event presented case studies and discussions as to how and why achieving savings, offsetting your demands and identify opportunities for recycling/recovery of energy and water is so important to Wales. The programme had three sections: Savings; Innovation and Offsets. Presentations from stakeholders such as Cadiff University, Centre for Alternative Technologies, Waterwise, Dulas, Bangor University Sustainability Lab, Adnams Southwold Brewery, Aberyswith University as well as two interventions from Dwr Uisce team members were featured. | Event | Transdisciplinary
54 | 8 | 20 | 20 | Delivered in collaboration with the National Federation of Group Water Schemes (Ireland). The workshop's objective were: - To present, discuss and learn from some of actual case-studies in the area of energy recovery from water distribution systems and wastewater systems, using hydropower turbines, pump optimisation and leakage reduction. - To build on the research connections between members of Group Water Schemes in Ireland and the Dŵr Uisce project team, legislators and technology providers. - To explore opportunities for energy recovery within the member schemes and implementation challenges. - To create new learning opportunities and connections for workshop participants. | Event | Transdisciplinary
55 | 8 | 26 | 26 | The second annual Dwr Uisce conference was hosted by Trinity College Dublin in Ireland. The theme was 'Water–Energy Innovation' and it addressed the challenges we face in relation to water and energy demands in our region. The programme included three sessions: "Innovation Opportunities", "Innovation Practice" and "Demonstrating Learning". The event featured a variety of guest speakers from industry, HEI and government sectors in Ireland and Wales. Participants were offered the opportunity to present two-minutes pitches of their water-energy related business or research. | Event | Transdisciplinary
56 | 6 | 65 | 78 | Competition programme for key stage 4 and 5 students in Welsh secondary schools. | Project | Interdisciplinary
57 | 6 | 60 | 78 | Exploring and quantifying the climate action potential from household water-related energy efficiency and contributions from emissions savings on Irish net-zero ambitions and targets. | Project | Interdisciplinary
58 | 8 | 58 | 60 | An in person event to launch our Citizen Science project and gather feedback from a community. | Event | Interdisciplinary
59 | 8 | 56 | 58 | The Climate Action Hackathon was a 2 -day online event to engaged teenagers aged 15-17 in ideating solutions for water-energy inefficiency. The event was led by Dwr Uisce team members and organised in collaboration with ECO-UNESCO in Dublin. During the 1 hr long pre-hackathon, participants had an opportunity to ask questions to Dwr Uisce team members about their work, the water-energy nexus and the project overall. The hackathon took place on the second day and the participants had 3 hours to work in teams to plan, design and present to the organisers and the other teams an idea that could improve the efficiency of water-related energy use in their schools, cmmunities or on a broader scale. Dwr Uisce team members acted as mentors, providing support and suggesitons throughout the event. | Event | Interdisciplinary
60 | 2 | 53 | 78 | Analyzing the difference in available wastewater heating resource across the different scales of an urban wastewater system i.e. how much heat is loss to the environment and does it build a case for decentralized wastewater heat recovery? | Project | Single Discipline
61 | 6 | 30 | 42 | Assessing the water-energy efficiency of wet leisure centre stock of a local authority in North Wales. | Project
62 | 6 |  |  | Assessment and quantification of the water use efficiency and management on resource use in participating schools | Project
63 | 7 | 19 | 52 | Study investigating how future worst-case scenario climate change will impact on the timing and quantity of streamflow at 130 catchment accross the UK and Ireland (currently England, Wales, Ireland & Northern Ireland), and the knock-on implications of such changes for water abstraction at 420 hydropower locations. | Project
64 | 8 | 46 | 66 | Journal article based upon a conference paper presented at IPDMC 2020. Describe and reflect on the actions undertaken by a network of stakeholders to co-generate learning from green process innovation. | Publication | Interdisciplinary
65 | 4 | 50 | 62 | Study investigating cost-effectiveness and emissions savings from replacing conventional heating systems (gas, oil, electricity, LPG and coal) to low-carbon heating systems (ASHP, GSHP, biomass boilers solar PV) | Publication
66 | 8 | 67 | 68 | We carried out a focus group with a gropu of transition year students to develop the materials for the hackathon porgamme | Project | Transdisciplinary
67 | 5 | 14 | 35 | Journal article investigating economic and environmental efficiency of water and sewage companes, with a focus on appropriate methodologies and the factors affecting performance | Publication | Interdisciplinary
68 | 5 | 36 | 49 | Journal article investigating energy and economic efficiency across water and sewage and water-only companies. Additional focus on assessing how common proxy indicators performed vs. best available | Publication | Interdisciplinary
69 | 5 | 50 | 58 | Journal article investigating the productivity of the UK water sector over a 6 year period using metrics based on a wider sustainability perspective. | Publication | Interdisciplinary
70 | 5 | 59 | 64 | Journal article evaluating the energy consumption of wastewater utilities across the globe | Publication | Single Discipline
71 | 5 | 65 | 74 | Journal article investigating the efficiency of water and sewage, communication, and energy utilties | Publication | Interdisciplinary
72 | 1 | 6 | 9 | Analysis of the water network operated by the Ballacolla GWS to assess the potential for hydro energy recovery | Study | Single Discipline
73 | 1 | 6 | 9 | Analysis of the water network operated by the Blackstairs GWS to assess the potential for hydro energy recovery | Study | Single Discipline
74 | 1 | 6 | 9 | Analysis of the water network operated by the Ballinabrannagh GWS to assess the potential for hydro energy recovery | Study | Single Discipline
75 | 1 | 6 | 9 | Analysis of the water network operated by the Kilanerin GWS to assess the potential for hydro energy recovery | Study | Single Discipline
76 | 1 | 9 | 11 | Analysis of three water networks operated by EPS to assess the potential for hydro energy recovery | Study | Single Discipline
77 | 1 | 12 | 13 | Analysis of a series of water networks and roadside culverts owned by the Blaenau Gwent municipality to assess the potential for hydro energy recovery | Study | Single Discipline
78 | 1 | 1 | 3 | Analysis of the outfall of the Five Fords WWTP operated by Welsh Water to assess the potential for hydro energy recovery and produce a preliminary design of the hydro site | Study | Single Discipline
79 | 1 | 21 | 22 | Analysis of the Dodder water supply line operated by Dublin City Council on behalf of Irish Water to assess the potential for hydro energy recovery | Study | Single Discipline
80 | 1 | 12 | 14 | Preliminary design of a picoturbine at the inlet of a storage tank in the Blackstairs GWS | Study | Single Discipline
81 | 1 | 45 | 47 | Analysis of a pressure reducing station at Boliden Tara Mines to assess the potential for hydro energy recovery | Study | Single Discipline
82 | 1 | 41 | 43 | Analysis of the outfall of the Dairygold WWTP to assess the potential for hydro energy recovery | Study | Single Discipline
83 | 1 | 43 | 44 | Analysis of the inlet of the Fethard WTP to assess the potential for hydro energy recovery | Study | Single Discipline
84 | 4 | 31 | 64 | Publication of the research on the development of a heat recovery toolkit for commercial kitchen owners (pubs, restaurants, cafes, canteens etc.) whcich enables them to get an estimate on their individual heat recovery potential from drain water, environmental and cost savings (or trade-offs). | Publication | Interdisciplinary
85 | 2 | 65 | 78 | Assess the feasibility of installaing a DWHR system at the Imperial Hotel, Llandudno | Project | Transdisciplinary
86 | 7 | 65 | 78 | Study investigating the impact of variation in abstraction licence conditions between England, Wales, Scotland, Northern Ireland, and Ireland on water abstraction for run-of-river hydropower. Study looks at the lost abstraction, and therefore power generation both historically (1985-2015) and for future worst-cast scenario climate change (RCP8.5) affected flows (2021-2080) | Project | Single Discipline
87 | 7 | 56 | 57 | Hydrological modelling work completed for the Talybont Community Flood Group to identify sub-catchments upstream of the village that are contributing the most to peak flows. Also studied was the impact of tree planting on reducing these peak flood flows. | Study | Transdisciplinary
88 | 4 | 69 | 71 | Consultation work for Aber Falls distillery on how to lower their environmental footprint with focus on energy, water use and by-product use. | Project | Transdisciplinary
89 | 8 | 74 | 74 |  | Event
90 | 8 | 74 | 74 |  | Event
91 | 8 | 68 |  |  | Project
92 | 2 | 16 | 44 | "Feaibility studies for DWHR at the following sites: National Trust, Coolmore Park GWS,Talbot Hotel Stillorgan,Druids Glen Hotel, Ashlawn Nursing Home, Nenagh Swimming Pool, Cooleney Cheese, ABP Food Group, Noel Lawlor Consulting Engineers" | Study
93 | 5 | 25 | 25 |  | Study
94 | 1 | 15 | 20 | Analysis of the water network operated by the Ballinguiroe Tankardstown GWS and Coolagh Caherleske GWS, Kilcredan GWS to assess the potential for hydro energy recovery | Study | Single Discipline
95 | 1 | 25 | 25 | Hydropower potential assessment of the Mullins Mill on the River Kings in Co. Kilkenny | study | Single Discipline
96 | 8 | 75 | 78 | Delivery of the Hackathon Programme in Irish Secondary Schools | Project
97 | 4 | 25 | 75 | Data collection for the whole production life cycle of whisky at Arbikie distillery, calculation of an environmental footprint and elaboration of suitable measures to reduce the carbon and water footprint by: using by-products or recovering heat from waste and process streams. | Project | Inter- and Transdisciplinary
98 | 7 | 22 | 22 |  | Study
99 | 1 | 10 | 10 |  | Study

## work packages
id | category | location test
WP_1 | Technology platfroms | france
WP_2 | Technology platfroms | ierland
WP_3 | Technology platfroms | wales
WP_4 | Policy Support and Guidance | germany
WP_5 | Policy Support and Guidance | portugal
WP_6 | Policy Support and Guidance | swizerland
WP_7 | Policy Support and Guidance | holland
WP_8 | Dissemination and Collaboration | england

## stakeholders
|  | Sector | Enterprise Category | Assign Level of engagement (0-none; 1-inform; 2 consult; 3-share; 4- cocreate) to stakeholders who participating
| Start Month |  |  | 2 | 14 | 18 | 20 | 26 | 33 | 39 | 63 | 60 | 54 | 54 | 55 | 55 | 56 | 62 | 68 | 12 |  |  | 1 | 1 | 67 | 57 | 67 | 56 | 69 | [8 empty] | 12 |  |  |  |  | 64 | [5 empty] | 65 | [7 empty] | 75 |  |  | 10
| Activity Name |  |  | Kick-Off meeting | First Annual Conference: 'Sustainability in Energy & Water Resources: Research & Practice' , 27 October 2017 | Enhancing the Resilience of your Welsh Organisation: Achieving Water and Energy Savings, 26 Feb 2018 | Water & Energy in Rural Communities. A workshop for Group Water Schemes in Ireland, 26 April 2018 | Second Annual Conference: ' Water-Energy Innovation'. 23 October 2018 | Launch of Blackstairs Demonstration site | T? Mawr Wybrnant Pico Hydropower Demonstration Site Launch | EPANET | Engagement Event - Citizen Science Project on Water-Energy Efficiency in Irish Households | Expert panel discussion on heat recovery potential of leisure centres | Sustainability Webinar on MHP | Drain Water Heat Recovery Webinar | Heat recovery in commercial kitchens Webinar | Benchmarking Webinar | Webinar: Impacts of climate change on future water availability for hydropower and public water supply in Wales, UK | Heat Recovery Tool Webinar- 2 | Blackstairs GWS micro-hydropower installation | Design and Implementation of ABP Food demonstration site | ABP Food monitoring | Ty Mawr Wybrnant GWS micro-hydropower installation | Design and implementation of DWHR system at Penrhyn Castle | NFGWS Primary School Workshops | Primary School Webinars (BGWS) | Climate Action Hackathon Programme in Irish Secondary School - Focus Group | Climate Action Hackathon with ECO-UNESCO | Carbon, water footprint and heat recovery assessment for Aber Falls distillery and consultation on how environmental footprint can be reduced. | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Ballacolla network | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Blackstairs network | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Ballinabrannagh network | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case study: Kilanerin network | EPS Hydropower Potential Feasibility Assessment: Drogheda WWTP, Blackstairs WTP, Cork Lower Harbour | Hydro Project Blaenau Gwent Pre feasibility study | Five Fords Hydropower site - Preliminary design | Dublin City Council Hydropower potential feasibility assessment Dodder Water Supply Scheme | Preliminary design of a hydropower energy recovery scheme Case study: Rathnure tank inlet | Tara Mines hydro feasibility assessment | Dairygold WWTP hydro feasibility assessment | Fethard WTP hydro feasibility assessment | Imperial Hotel DWHR Assessment | Monitoring of the Rediscovery Centre grease trap and feasibility report for DWHR | Improving water-related energy efficiency in wet leisure centres in Denbighshire County Council (DCC). | Heat recovery potential of leisure centres (Calon Tysul leisure centre - Ceredigion). | Water-energy efficiency of commercial swimming pools (6 x Welsh leisure centres in collaboration with Pool Sentry). | Water-energy efficiency in offices (M-Sparc: Menai Science Park). | Water-energy efficiency of Gibney's pub in Dublin | Bangor University Student Accommodation monitoring | Consultation and modelling work for Talybont Community Flood Group constituting an assessment of sub-basin contributions to peak flows at Talybont in the Afon Leri catchment, and the potential impact of tree planting on streamflow. | Launch of Penrhyn Demonstration site in person | Launch of Penrhyn Demonstration site online | Drain Water Heat Recovery Fesibility Studies | GIS and water industry statistic based study to explore the effect of rurality on energy consumption in water supply services | Feasibility of MHP generation in community-owned rural water supply networks in Ireland Case studies: Ballinguiroe Tankardstown GWS, Coolagh Caherleske GWS, Kilcredan GWS, Killally Ballinrush GWS and Kilriffith Kilmore GWS and Walterstown GWS (plus Moyne and Patrickswell GWSs - unfinished) | Mullins Mill, Kells, County Kilkenny Hydropower potential assessment | Climate Action Hackathon Programme in Irish Secondary School - Delivery | Studying water, energy and material use as well as energy and resource recovery options in a micro-distillery, focussing on by-product streams and water heat recovery. | Hydrological modelling assessment in the Afon Gwyrfai catchment to quantify flooding impacts | Preliminary design of a 4KWh pico hydro scheme powered by a pump-as-turbine
S_ID | Organisation/Activity ID |  |  | 51 | 52 | 53 | 54 | 55 | 31 | 27 | 35 | 58 | 37 | 6 | 43 | 14 | 47 | 20 | 50 | 1 | 45 | 46 | 2 | 12 | 42 | 25 | 66 | 59 | 88 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 85 | 49 | 36 | 38 | 39 | 40 | 41 | 48 | 87 | 89 | 90 | 92 | 93 | 93 | 95 | 96 | 97 | 98 | 99
S_1 | 9 Meals From Anarchy | Industry | Food | [11 empty] | 2
S_2 | Aber falls distillery | Industry | Beverage | [25 empty] | 3
S_3 | ABP Food Group | Industry | Food |  |  |  |  | 2 | [12 empty] | 3 | 3 | [30 empty] | 2
S_4 | Action Renewables | Professional, administration and support services | Consultancy |  | 3 |  |  | 2 | [43 empty] | 2
S_5 | Adnams Brewery and Distillery | Industry | Beverage | 3 | 3
S_6 | AEC | No-profit institution | Professional Association |  |  |  |  | 2
S_7 | Aramark Northern Europe | Professional, administration and support services | Customer services |  |  |  |  | 2
S_8 | ARUP | Professional, administration and support services | ARUP |  | 3 |  | 2
S_9 | Ashlawn Nursing Home | Health care | Ashlawn Nursing Home | [49 empty] | 2
S_10 | Auralab | Professional, administration and support services | Auralab | 3
S_12 | Ballinabranna Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2 | [13 empty] | 4 | [6 empty] | 2
S_14 | Ballingate Group Water Scheme | Utility | Water provider | [5 empty] | 3
S_15 | Ballinguiroe Tankardstown GWS | Utility | Water provider | [51 empty] | 2
S_16 | Ballyshannon Leisure Centre | Sport Facilities | Ballyshannon Leisure Centre | [9 empty] | 3
S_19 | Birchfield Farm | Agriculture | Birchfield Farm |  |  | 3
S_20 | Black & Veatch | Professional, administration and support services | Consultancy | [50 empty] | 3
S_21 | Black Boy Inn | Hospitality | Black Boy Inn | [12 empty] | 2
S_22 | Blackstairs Group Water Scheme | Utility | Water provider |  |  |  | 2 | 2 | 3 |  | 2 | [8 empty] | 4 |  |  |  |  | 4 | 4 |  |  |  |  | 2
S_23 | Blaen Eidda Ysbyty Ifan | Agriculture | Blaen Eidda Ysbyty Ifan | [6 empty] | 3
S_24 | Blaenau Gwent County Borough Council | General Government | Local authority |  | 3 | [29 empty] | 2 |  |  | 2
S_25 | BlueTech Research | Education | Higher Education |  |  |  |  | 2
S_26 | Boliden Tara Mines | Industry | Mining | [35 empty] | 2
S_27 | Bon Secours Hospital Galway | Health care | Hospital | [10 empty] | 2
S_28 | Borrmont GWS | Utility | Water provider | [7 empty] | 2
S_29 | BPD Limited | Industry | Plumbing and heating |  |  |  |  | 2
S_30 | Brandon House Hotel | Hospitality | Brandon House Hotel | [15 empty] | 2
S_31 | Bring It To The Lab | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_32 | Bundoran Waterworld CLG | Sport Facilities | Leisure Centre | [9 empty] | 3
S_33 | Business and Industry Committee, RDS | No-profit institution | Charity | 3
S_34 | Byw'n Iach | Sport Facilities | Leisure Centre | [9 empty] | 3 | [32 empty] | 2
S_36 | Calon Tysul | Sport Facilities | Leisure Centre | [9 empty] | 3 | [31 empty] | 4
S_37 | Cardiff University | Education | Higher Education |  | 3 | 3
S_38 | Carlow County Council | General Government | Local authority |  |  |  | 2
S_39 | Carlow IT | Education | Higher Education | 3
S_40 | Caulmert Ltd | Professional, administration and support services | Consultancy |  |  | 3
S_41 | Centre for Alternative Technology Wales | Education | Higher Education | [6 empty] | 3
S_42 | Club Vitae Oranmore, Galway | Sport Facilities | Leisure Centre | [9 empty] | 3
S_43 | Codema | No-profit institution | Agency | [11 empty] | 2
S_44 | Colman Hession and Associates Engineers | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_45 | Commission for Energy Regulation | General Government | Government agency | 3
S_46 | Commission for Regulation of Utilities | General Government | Government agency |  | 3 |  |  | 2
S_47 | Consumer Council for Water | General Government | Government agency |  | 3
S_48 | Coolagh Caherleske GWS | Utility | Water provider | [51 empty] | 2
S_49 | Cooleeney Cheese | Agriculture | Farm
S_50 | Coolmore Park GWS | Utility | Water provider
S_51 | Co-Operative Housing Ireland (CHI) | General Government | Approved Housing Body | [8 empty] | 3
S_52 | Coral Leisure killarney | Sport Facilities | Leisure Centre | [9 empty] | 3
S_53 | Coral Leisure Ltd | Sport Facilities | Leisure Centre | [9 empty] | 3 | 2 | 2 | 2 | 2
S_54 | Corwn Leisure Centre | Sport Facilities | Leisure Centre | [40 empty] | 3
S_55 | Cosyn Cymru | Industry | Dairy | [10 empty] | 2
S_56 | Cullahill/Seskin GWS | Utility | Water provider | [7 empty] | 2
S_57 | Cully Automation | Professional, administration and support services | Consultancy |  |  |  | 2 | 2
S_58 | Cwrw Lyn Brewery | Industry | Beverage
S_59 | Cyfoeth Naturiol Cymru / Natural Resources Wales | General Government | Government agency |  | 3 | 3 |  |  |  | 3 | [6 empty] | 2 | [34 empty] | 2
S_60 | Cyngor Gwynedd Council | General Government | Local authority |  | 3 | [7 empty] | 3 | [32 empty] | 2
S_61 | Dairygold | Industry | Dairy | [36 empty] | 2
S_62 | DCU | Education | Higher Education |  |  |  | 2 | 2
S_63 | Dean of Research TCD | Education | Higher Education | 3
S_64 | Denbighshire County Council | General Government | Local authority | [40 empty] | 2 |  | 2
S_65 | Denbighshire Leisure | Sport Facilities | Leisure Centre | [40 empty] | 2 |  | 2
S_66 | Department of Housing, Planning, Community & Local Government | General Government | Government department | 3 |  |  | 2 |  | 3 | [10 empty] | 1
S_67 | Detectronic Ltd | Professional, administration and support services | Consultancy |  | 3
S_68 | Donal Mc Kenna | Professional, administration and support services | Consultancy | [11 empty] | 2 | 2
S_69 | Driftwood Experience Ltd | Hospitality | Café | [12 empty] | 2
S_70 | Druids Glen Hotel | Hospitality | Hotel | [49 empty] | 2
S_71 | Dublin City Council | General Government | Local authority |  |  |  |  | 2 | [28 empty] | 2
S_72 | Dulas Ltd | Professional, administration and support services | Consultancy | 3 | 3 |  |  |  |  | 3
S_73 | Dunne Technical Services | Professional, administration and support services | Consultancy | [5 empty] | 3
S_74 | Dwr Cymru Welsh Water (DCWW) | Utility | Water provider | 3 | 3 | 3 |  | 2 |  | 3 | [7 empty] | 2 | [17 empty] | 2 | [17 empty] | 1
S_76 | Egnida | Professional, administration and support services | Consultancy |  |  | 3
S_77 | EIP on Water / Baur Technology | European body | Agency | 3
S_78 | Energy Elephant | Professional, administration and support services |  | 3
S_79 | Energy Saving Trust | Professional, administration and support services | Consultancy | 3
S_80 | Engineers Ireland | No-profit institution | Professional Association |  |  |  |  | 2
S_81 | ENICA Ltd | Professional, administration and support services | Technology |  |  | 3 | [16 empty] | 4
S_82 | Epro Advance Technology Ltd | Utility | Energy provider | [13 empty] | 2
S_83 | EPS Group | Professional, administration and support services |  | 3 |  |  |  | 2 | 3 |  |  |  |  | 2 |  |  | 2 |  |  | 4 | [13 empty] | 2
S_84 | Feedzai | Financial and insurance activities | Risk management | [11 empty] | 2
S_85 | Fermanagh Omagh District Council | General Government | Local authority | [9 empty] | 3
S_86 | Finance, Bangor University | Education | Higher Education | 3
S_87 | Fingleton White | Professional, administration and support services | Consultancy | [10 empty] | 2
S_88 | Flintshire County Council | General Government | Local authority | [10 empty] | 2
S_89 | Food Technology Centre | Professional, administration and support services | Consultancy |  |  | 3
S_90 | Forta Pro | Constrution | Building company | [10 empty] | 2
S_91 | Forterra | Constrution | Building materials |  |  | 3
S_92 | Gas Networks | Utility | Energy provider |  |  |  |  | 2
S_93 | General Public | Households | General public |  |  |  |  | 2 |  | 3 | [7 empty] | 2
S_95 | GIP Campus | Education | Higher Education | [11 empty] | 2 | 2
S_96 | Glan Agua | Professional, administration and support services | Consultancy | [37 empty] | 2
S_97 | GLL | Sport Facilities | Leisure Centre | [9 empty] | 3
S_98 | Glynn St. Mullins Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2
S_99 | Green Connection | Professional, administration and support services | Consultancy | [13 empty] | 2
S_100 | H2 Ozone | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_101 | HC Financial Training | Financial and insurance activities | Consultancy | 3
S_102 | Heath Group Water Scheme | Utility | Water provider |  |  |  | 2 | 2
S_103 | Higher Education Authority (HEA) | General Government | Statuatory body | 3
S_104 | Hinds book shop | Retailing | Book shop |  |  |  |  | 2
S_105 | Hogg Enterprises | Agriculture | Support service | [5 empty] | 3
S_106 | HSE | General Government | Agency | [10 empty] | 2 | 2 | 2
S_107 | IBERS | Education | Higher Education |  |  | 3
S_108 | Imperial Hotel Galway | Hospitality | Hotel | [15 empty] | 2
S_109 | Imperial Hotel Llandundo | Hospitality | Hotel | [38 empty] | 2
S_110 | Innogy Renewables uk | Industry | Manufacturing |  |  | 3
S_111 | International Hotel Killarney | Hospitality | Hotel | [15 empty] | 2
S_112 | Interreg Ireland-Wales Programme | General Government | Agency | 3
S_113 | Ireland-Wales PSC | General Government | Agency | 3
S_114 | Irish Rail | Transport | Company |  |  |  |  | 2
S_115 | Irish Water | Utility | Water provider | 3 |  |  |  | 2 | [8 empty] | 2 | 2
S_116 | JLA Hydro | Professional, administration and support services | Consultancy | [10 empty] | 2 | 2 | 2 | 2
S_117 | Kerry County Council | General Government | Local authority | 3 | [8 empty] | 3
S_118 | Kilanerin Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2 | [21 empty] | 2
S_119 | Kilcredan GWS | Utility | Water provider | [51 empty] | 2
S_120 | Kildare County Council | General Government | Local authority | [5 empty] | 3
S_121 | Kilkenny County Council | General Government | Local authority |  |  |  | 2
S_122 | Killally Ballinrush GWS | Utility | Water provider | [51 empty] | 2
S_123 | Kilriffith Kilmore GWS | Utility | Water provider | [51 empty] | 2
S_124 | Kings Mill Kilkenny | Entertainment | Heritage site | [52 empty] | 2
S_125 | Langton House Hotel | Hospitality | Hotel | [15 empty] | 2
S_126 | Laois County Council | General Government | Local authority | [5 empty] | 3
S_127 | Lovegrove EBS Ltd | Professional, administration and support services | Consultancy |  |  | 3 | [6 empty] | 3 | 2 |  | 2
S_128 | Mark Eire BV | Professional, administration and support services | Technology | [9 empty] | 3
S_129 | Martin J Hughes Glas Cymru | Utility | Water provider | [11 empty] | 2 | [35 empty] | 2
S_130 | Mayo County Council | General Government | Local authority | [9 empty] | 3
S_131 | Mbarara University of Science and Technology | Education | Higher Education | [12 empty] | 2
S_132 | Menai Science Park | Professional, administration and support services | Business support | [43 empty] | 3
S_133 | Moyne GWS | Utility | Water provider | [51 empty] | 1
S_134 | Mullaun Group Water Scheme | Utility | Water provider | [5 empty] | 3 |  | 2
S_135 | Narraghmore Group Water Scheme | Utility | Water provider |  |  |  | 2
S_136 | National Council of Ireland | General Government | Agency |  |  |  |  | 2
S_137 | National Federation of Group Water Schemes (NFGWS) | Utility | Water provider | 3 | 3 |  | 2 | 2 | 3 |  | 2 |  |  | 2 | [5 empty] | 3 |  |  |  |  | 3 | 3
S_138 | National Research Network - Low Carbon Energy & Environment | Education | Higher Education | 3
S_139 | National Trust (NT) | No-profit institution | Charity | [6 empty] | 3 | [12 empty] | 3 | 3 | [26 empty] | 3 | 2 | 2
S_140 | National Trust Wales | No-profit institution | Charity | 3 | 3 | [17 empty] | 4 | 4 | [26 empty] | 3 | 2 | 2
S_141 | Nenagh Swimming Pool | Sport Facilities | Leisure Centre | [49 empty] | 2
S_142 | Neville Park Hotels | Hospitality | Hotel | [15 empty] | 2
S_144 | Nicholas O'Dwyer Ltd | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_145 | Noel Lawlor Consulting Engineers | Professional, administration and support services | Consultancy | [49 empty] | 2
S_146 | Nova Centre Prestatyn | Sport Facilities | Leisure Centre | [40 empty] | 3 |  | 4
S_147 | NTC - Nexus Technologies Concepts | Professional, administration and support services | Consultancy | [10 empty] | 2 |  |  | 2
S_148 | NUI Galway | Education | Higher Education |  | 3
S_149 | Ogwen Hydro | Professional, administration and support services | Consultancy | [56 empty] | 2
S_150 | Operational Support Services Limited | Professional, administration and support services | Consultancy |  | 3
S_151 | OzoneTech | Professional, administration and support services | Technology |  |  |  |  | 2
S_152 | Pant Glas Padog Conwy | Agriculture | Farm | [6 empty] | 3
S_153 | Parkwood Leisure | Sport Facilities | Leisure Centre | [9 empty] | 3
S_154 | Patrickswell GWS | Utility | Water provider | [51 empty] | 1
S_155 | PepsiCo Ireland | Industry | Beverage | [49 empty] | 2
S_156 | Pool Sentry | Sport Facilities | Leisure Centre | [9 empty] | 3 | [32 empty] | 4
S_157 | Portarlington Leisure Centre | Sport Facilities | Leisure Centre | [9 empty] | 3
S_158 | Portmagee Whiskey distillery | Industry | Beverage
S_159 | Q -Blue BV | Industry | Manufacturing |  |  |  |  | 2 | [10 empty] | 2
S_160 | Rain Surfer | Professional, administration and support services | Technology |  |  |  |  | 3
S_162 | Rhyl Leisure Centre | Sport Facilities | Leisure Centre | [40 empty] | 3 |  | 4
S_163 | Roscommon City Council | General Government | Local authority |  |  |  | 2
S_164 | RPS Group | Professional, administration and support services | Consultancy | 3 |  |  |  | 2 | [5 empty] | 2
S_165 | Ruthin Leisure Centre | Sport Facilities | Leisure Centre | [40 empty] | 3
S_166 | Ryan Hanley Ltd | Professional, administration and support services | Consultancy |  |  |  |  | 2
S_167 | Saudi Aramco | Industry | Oil | [10 empty] | 2
S_168 | SC2 leisure centre | Sport Facilities | Leisure Centre | [40 empty] | 3 |  | 4
S_169 | Shannon Swimming & Leisure Centre | Sport Facilities | Leisure Centre | [9 empty] | 3
S_170 | shri Ram Rayons | Industry | Manufacturing | [13 empty] | 2
S_171 | Siemens | Industry | Technology |  |  |  |  | 2
S_172 | Southern Regional Assembly | General Government | Agency |  |  |  | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 |  | 2 | [32 empty] | 2
S_174 | Sustainability Lab | Education | Higher Education | [6 empty] | 3
S_175 | Sustainable Energy Authority of Ireland | General Government | Agency |  | 3
S_176 | Sustainable Travel Ireland | Professional, administration and support services | Tourism | [15 empty] | 2
S_177 | Talbot Hotel Group | Hospitality | Hotel | [15 empty] | 2
S_178 | Talbot Hotel Stillorgan | Hospitality | Hotel | [49 empty] | 2
S_179 | Tan y Lan Fach | Hospitality | Accommodation | [10 empty] | 2 | 2 | 2 | 2
S_180 | TCFG | No-profit institution | Community | [46 empty] | 2
S_181 | Technological University Dublin | Education | Higher Education | [10 empty] | 2 | 2 |  | 2
S_182 | Temple Gate Hotel | Hospitality | Hotel | [15 empty] | 2
S_183 | The Brown's | Hospitality | Hotel |  |  | 3
S_184 | The Brunner CBS | Education | Higher Education | [53 empty] | 2
S_185 | The Clanard Court Hotel | Hospitality | Hotel | [15 empty] | 2
S_186 | The Grand Hotel Dublin | Hospitality | Hotel | [15 empty] | 2
S_187 | The Green Valleys CIC | No-profit institution | Community | [10 empty] | 2
S_188 | The Rediscovery Centre | No-profit institution | Charity | [12 empty] | 2 | [26 empty] | 2
S_189 | The Savoy Hotel | Hospitality | Hotel | [15 empty] | 2
S_190 | The Start | Hospitality | Accommodation |  |  | 3
S_191 | The University of the West of England | Education | Higher Education |  | 3
S_192 | The Watershed | Sport Facilities | Leisure Centre | [9 empty] | 3
S_193 | The Watershed Kilkenny | Sport Facilities | Leisure Centre | [9 empty] | 3
S_194 | Tipperary County Council | General Government | Local authority |  |  |  | 2 | 2 | 3 |  |  |  |  | 2
S_196 | UCD | Education | Higher Education |  |  |  |  | 2
S_197 | UMNG | Education | Higher Education | [13 empty] | 2
S_198 | Universidad de Valencia | Education | Higher Education | [10 empty] | 2 | 2 |  | 2
S_199 | Universitat Jaume I | Education | Higher Education |  |  |  |  | 2
S_200 | University of Cordoba | Education | Higher Education | 3 | 3
S_201 | University of the Philippines | Education | Higher Education | [12 empty] | 2
S_202 | VEOLIA Environmental Services Technical Solutions Limited | Professional, administration and support services | Consultancy | 3
S_203 | Verde Environmental Consulting | Professional, administration and support services | Consultancy | [10 empty] | 2
S_204 | volunteer | Households | General public | [14 empty] | 2
S_205 | Walterstown GWS | Utility | Water provider | [51 empty] | 2
S_206 | Watef Network | No-profit institution | Network | 3 | 3
S_207 | Water CoLab | Professional, administration and support services | Business support |  |  |  |  | 2
S_208 | Water Loss Research & Analysis Ltd | Professional, administration and support services | Consultancy |  | 3
S_209 | Water Turbines PLC | Constrution | Infrastructure | 3 | 3
S_210 | Waterford County Council | General Government | Local authority |  |  |  | 2
S_211 | Waterways Ireland | General Government | Agency | [10 empty] | 2
S_212 | Waterwise | No-profit institution | Advocacy | 3
S_213 | Welsh Assembly | General Government | Government department |  | 3
S_214 | Welsh Government | General Government | Government department |  |  | 3 | [7 empty] | 2 | 2 | 2 | 2 | 2 | [33 empty] | 2
S_215 | WEW Consulting | Professional, administration and support services | Consultancy | [5 empty] | 3
S_216 | Wexford City Council | General Government | Local authority |  |  |  | 2
S_217 | Wexford County Council | General Government | Local authority | [5 empty] | 3 | [10 empty] | 1
S_218 | Wicklow County Council | General Government | Local authority |  |  |  | 2 |  | 3
S_219 | Wicklow Uplands council | No-profit institution | Voluntary organisation | [10 empty] | 2 |  | 2
S_220 | Woodford Dolmen Hotel | Hospitality | Hotel | [15 empty] | 2
S_221 | Yangzhou university | Education | Higher Education | [14 empty] | 2
S_222 | Ymgynghoriaeth Gwynedd Consultancy | Professional, administration and support services | Consultancy | [55 empty] | 2
S_223 | Ynni Llyn - community energy scheme | No-profit institution | Community | [6 empty] | 3
S_224 | Ynni Ogwen | Utility | Energy provider | [6 empty] | 3
S_225 | Ynys Resources Ltd | Professional, administration and support services | Consultancy |  | 3
S_226 | Arbikie Distillery | Industry | Beverage | [54 empty] | 4
S_161 | Rathnure National School | Education | Primary Education | [21 empty] | 3 | 3
S_35 | Caim National School | Education | Primary Education | [21 empty] | 2 | 2
S_173 | St Joseph Donard National School | Education | Primary Education | [21 empty] | 2 | 2
S_13 | Ballinabranna National School | Education | Primary Education | [21 empty] | 3
S_143 | Newpark Comprehensive School | Education | Secondary education | [23 empty] | 4
S_75 | ECOUNESCO | No-profit institution | Charity | [24 empty] | 3
S_11 | Ballacolla Group Water Scheme | Utility | Water provider | [26 empty] | 2
S_94 | Gibneys of Malahide | Hospitality | Pub | [44 empty] | 3
S_227 | Mountain Studios | Utility | Water provider | [47 empty] | 2
S_228 | The Royal Victoria Hotel | Utility | Water provider | [47 empty] | 2
S_229 | Geosmart Decision | Utility | Water provider | [48 empty] | 2
S_230 | University of Bath | Utility | Water provider | [48 empty] | 2
S_231 | University of Exeter | Utility | Water provider | [48 empty] | 2
S_232 | Pforzheim University (Germany) | Utility | Water provider | [48 empty] | 2
S_233 | Northumbrian Water | Utility | Water provider | [48 empty] | 2
S_18 | Bangor University St Mary's Student Accommodation | Hospitality | Bangor University St Mary's Student Accommodation | [45 empty] | 2
S_234 | Arfon Leisure Centre | Sport Facilities | Leisure Centre | [42 empty] | 4
S_235 | Bangor Leisure Centre | Sport Facilities | Leisure Centre | [42 empty] | 4
S_236 | Glaslyn Leisure Centre | Sport Facilities | Leisure Centre | [42 empty] | 4

## stakeholder links
S_ID/ ACT_ID | 51 | 52 | 53 | 54 | 55 | 31 | 27 | 35 | 58 | 37 | 6 | 43 | 14 | 47 | 20 | 50 | 1 | 45 | 46 | 2 | 12 | 42 | 25 | 66 | 59 | 88 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 85 | 49 | 36 | 38 | 39 | 40 | 41 | 48 | 87 | 89 | 90 | 92 | 93 | 93 | 95 | 96 | 97 | 98 | 99
S_1 | [11 empty] | 2
S_2 | [25 empty] | 3
S_3 |  |  |  |  | 2 | [12 empty] | 3 | 3 | [30 empty] | 2
S_4 |  | 3 |  |  | 2 | [43 empty] | 2
S_5 | 3 | 3
S_6 |  |  |  |  | 2
S_7 |  |  |  |  | 2
S_8 |  | 3 |  | 2
S_9 | [49 empty] | 2
S_10 | 3
S_12 | [5 empty] | 3 |  | 2 | [13 empty] | 4 | [6 empty] | 2
S_14 | [5 empty] | 3
S_15 | [51 empty] | 2
S_16 | [9 empty] | 3
S_19 |  |  | 3
S_20 | [50 empty] | 3
S_21 | [12 empty] | 2
S_22 |  |  |  | 2 | 2 | 3 |  | 2 | [8 empty] | 4 |  |  |  |  | 4 | 4 |  |  |  |  | 2
S_23 | [6 empty] | 3
S_24 |  | 3 | [29 empty] | 2 |  |  | 2
S_25 |  |  |  |  | 2
S_26 | [35 empty] | 2
S_27 | [10 empty] | 2
S_28 | [7 empty] | 2
S_29 |  |  |  |  | 2
S_30 | [15 empty] | 2
S_31 |  |  |  |  | 2
S_32 | [9 empty] | 3
S_33 | 3
S_34 | [9 empty] | 3 | [32 empty] | 2
S_36 | [9 empty] | 3 | [31 empty] | 4
S_37 |  | 3 | 3
S_38 |  |  |  | 2
S_39 | 3
S_40 |  |  | 3
S_41 | [6 empty] | 3
S_42 | [9 empty] | 3
S_43 | [11 empty] | 2
S_44 |  |  |  |  | 2
S_45 | 3
S_46 |  | 3 |  |  | 2
S_47 |  | 3
S_48 | [51 empty] | 2
S_49
S_50
S_51 | [8 empty] | 3
S_52 | [9 empty] | 3
S_53 | [9 empty] | 3 | 2 | 2 | 2 | 2
S_54 | [40 empty] | 3
S_55 | [10 empty] | 2
S_56 | [7 empty] | 2
S_57 |  |  |  | 2 | 2
S_58
S_59 |  | 3 | 3 |  |  |  | 3 | [6 empty] | 2 | [34 empty] | 2
S_60 |  | 3 | [7 empty] | 3 | [32 empty] | 2
S_61 | [36 empty] | 2
S_62 |  |  |  | 2 | 2
S_63 | 3
S_64 | [40 empty] | 2 |  | 2
S_65 | [40 empty] | 2 |  | 2
S_66 | 3 |  |  | 2 |  | 3 | [10 empty] | 1
S_67 |  | 3
S_68 | [11 empty] | 2 | 2
S_69 | [12 empty] | 2
S_70 | [49 empty] | 2
S_71 |  |  |  |  | 2 | [28 empty] | 2
S_72 | 3 | 3 |  |  |  |  | 3
S_73 | [5 empty] | 3
S_74 | 3 | 3 | 3 |  | 2 |  | 3 | [7 empty] | 2 | [17 empty] | 2 | [17 empty] | 1
S_76 |  |  | 3
S_77 | 3
S_78 | 3
S_79 | 3
S_80 |  |  |  |  | 2
S_81 |  |  | 3 | [16 empty] | 4
S_82 | [13 empty] | 2
S_83 | 3 |  |  |  | 2 | 3 |  |  |  |  | 2 |  |  | 2 |  |  | 4 | [13 empty] | 2
S_84 | [11 empty] | 2
S_85 | [9 empty] | 3
S_86 | 3
S_87 | [10 empty] | 2
S_88 | [10 empty] | 2
S_89 |  |  | 3
S_90 | [10 empty] | 2
S_91 |  |  | 3
S_92 |  |  |  |  | 2
S_93 |  |  |  |  | 2 |  | 3 | [7 empty] | 2
S_95 | [11 empty] | 2 | 2
S_96 | [37 empty] | 2
S_97 | [9 empty] | 3
S_98 | [5 empty] | 3 |  | 2
S_99 | [13 empty] | 2
S_100 |  |  |  |  | 2
S_101 | 3
S_102 |  |  |  | 2 | 2
S_103 | 3
S_104 |  |  |  |  | 2
S_105 | [5 empty] | 3
S_106 | [10 empty] | 2 | 2 | 2
S_107 |  |  | 3
S_108 | [15 empty] | 2
S_109 | [38 empty] | 2
S_110 |  |  | 3
S_111 | [15 empty] | 2
S_112 | 3
S_113 | 3
S_114 |  |  |  |  | 2
S_115 | 3 |  |  |  | 2 | [8 empty] | 2 | 2
S_116 | [10 empty] | 2 | 2 | 2 | 2
S_117 | 3 | [8 empty] | 3
S_118 | [5 empty] | 3 |  | 2 | [21 empty] | 2
S_119 | [51 empty] | 2
S_120 | [5 empty] | 3
S_121 |  |  |  | 2
S_122 | [51 empty] | 2
S_123 | [51 empty] | 2
S_124 | [52 empty] | 2
S_125 | [15 empty] | 2
S_126 | [5 empty] | 3
S_127 |  |  | 3 | [6 empty] | 3 | 2 |  | 2
S_128 | [9 empty] | 3
S_129 | [11 empty] | 2 | [35 empty] | 2
S_130 | [9 empty] | 3
S_131 | [12 empty] | 2
S_132 | [43 empty] | 3
S_133 | [51 empty] | 1
S_134 | [5 empty] | 3 |  | 2
S_135 |  |  |  | 2
S_136 |  |  |  |  | 2
S_137 | 3 | 3 |  | 2 | 2 | 3 |  | 2 |  |  | 2 | [5 empty] | 3 |  |  |  |  | 3 | 3
S_138 | 3
S_139 | [6 empty] | 3 | [12 empty] | 3 | 3 | [26 empty] | 3 | 2 | 2
S_140 | 3 | 3 | [17 empty] | 4 | 4 | [26 empty] | 3 | 2 | 2
S_141 | [49 empty] | 2
S_142 | [15 empty] | 2
S_144 |  |  |  |  | 2
S_145 | [49 empty] | 2
S_146 | [40 empty] | 3 |  | 4
S_147 | [10 empty] | 2 |  |  | 2
S_148 |  | 3
S_149 | [56 empty] | 2
S_150 |  | 3
S_151 |  |  |  |  | 2
S_152 | [6 empty] | 3
S_153 | [9 empty] | 3
S_154 | [51 empty] | 1
S_155 | [49 empty] | 2
S_156 | [9 empty] | 3 | [32 empty] | 4
S_157 | [9 empty] | 3
S_158
S_159 |  |  |  |  | 2 | [10 empty] | 2
S_160 |  |  |  |  | 3
S_162 | [40 empty] | 3 |  | 4
S_163 |  |  |  | 2
S_164 | 3 |  |  |  | 2 | [5 empty] | 2
S_165 | [40 empty] | 3
S_166 |  |  |  |  | 2
S_167 | [10 empty] | 2
S_168 | [40 empty] | 3 |  | 4
S_169 | [9 empty] | 3
S_170 | [13 empty] | 2
S_171 |  |  |  |  | 2
S_172 |  |  |  | 2 | 2 | 3 |  |  |  |  | 2 | 2 | 2 | 2 |  | 2 | [32 empty] | 2
S_174 | [6 empty] | 3
S_175 |  | 3
S_176 | [15 empty] | 2
S_177 | [15 empty] | 2
S_178 | [49 empty] | 2
S_179 | [10 empty] | 2 | 2 | 2 | 2
S_180 | [46 empty] | 2
S_181 | [10 empty] | 2 | 2 |  | 2
S_182 | [15 empty] | 2
S_183 |  |  | 3
S_184 | [53 empty] | 2
S_185 | [15 empty] | 2
S_186 | [15 empty] | 2
S_187 | [10 empty] | 2
S_188 | [12 empty] | 2 | [26 empty] | 2
S_189 | [15 empty] | 2
S_190 |  |  | 3
S_191 |  | 3
S_192 | [9 empty] | 3
S_193 | [9 empty] | 3
S_194 |  |  |  | 2 | 2 | 3 |  |  |  |  | 2
S_196 |  |  |  |  | 2
S_197 | [13 empty] | 2
S_198 | [10 empty] | 2 | 2 |  | 2
S_199 |  |  |  |  | 2
S_200 | 3 | 3
S_201 | [12 empty] | 2
S_202 | 3
S_203 | [10 empty] | 2
S_204 | [14 empty] | 2
S_205 | [51 empty] | 2
S_206 | 3 | 3
S_207 |  |  |  |  | 2
S_208 |  | 3
S_209 | 3 | 3
S_210 |  |  |  | 2
S_211 | [10 empty] | 2
S_212 | 3
S_213 |  | 3
S_214 |  |  | 3 | [7 empty] | 2 | 2 | 2 | 2 | 2 | [33 empty] | 2
S_215 | [5 empty] | 3
S_216 |  |  |  | 2
S_217 | [5 empty] | 3 | [10 empty] | 1
S_218 |  |  |  | 2 |  | 3
S_219 | [10 empty] | 2 |  | 2
S_220 | [15 empty] | 2
S_221 | [14 empty] | 2
S_222 | [55 empty] | 2
S_223 | [6 empty] | 3
S_224 | [6 empty] | 3
S_225 |  | 3
S_226 | [54 empty] | 4
S_161 | [21 empty] | 3 | 3
S_35 | [21 empty] | 2 | 2
S_173 | [21 empty] | 2 | 2
S_13 | [21 empty] | 3
S_143 | [23 empty] | 4
S_75 | [24 empty] | 3
S_11 | [26 empty] | 2
S_94 | [44 empty] | 3
S_227 | [47 empty] | 2
S_228 | [47 empty] | 2
S_229 | [48 empty] | 2
S_230 | [48 empty] | 2
S_231 | [48 empty] | 2
S_232 | [48 empty] | 2
S_233 | [48 empty] | 2
S_18 | [45 empty] | 2
S_234 | [42 empty] | 4
S_235 | [42 empty] | 4
S_236 | [42 empty] | 4

## links
ID | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99
1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [24 empty] | 1
2 | 1 |  | 1 |  | 1 | 1 |  | 1 | [24 empty] | 1
3 | 1 | 1 | [30 empty] | 1
4 | 1 | [22 empty] | 1 |  |  | 1 | 1 |  | 1 |  |  | 1 | [7 empty] | 1 | [7 empty] | 1
5 | 1 | 1 | [30 empty] | 1
6 | 1 | 1 |  |  |  |  | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1 | [7 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | [9 empty] | 1 |  |  | 1
7 | 1 |  |  |  |  | 1 |  | 1 | [24 empty] | 1
8 | 1 | 1 |  | 1 |  | 1 | [26 empty] | 1
9 | [9 empty] | 1 | [22 empty] | 1
10 | [8 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [16 empty] | 1 | [15 empty] | 1 | [41 empty] | 1
11 | [14 empty] | 1 | [17 empty] | 1
12 | [9 empty] | 1 |  |  | 1 | 1 | 1 | 1 | [16 empty] | 1 | [8 empty] | 1 |  |  |  |  | 1 |  | 1 |  | 1
13 | [15 empty] | 1 | [16 empty] | 1
14 | [5 empty] | 1 |  |  | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 |  |  | 1 | [7 empty] | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 | [5 empty] | 1 |  |  |  | 1 |  |  | 1
15 | [11 empty] | 1 |  | 1 |  | 1 | [16 empty] | 1 | [15 empty] | 1
16 | [9 empty] | 1 |  | 1 | 1 | 1 | 1 | [17 empty] | 1 | [15 empty] | 1
17 | [32 empty] | 1 | [62 empty] | 1
18 | [32 empty] | 1 | [32 empty] | 1
20 | [5 empty] | 1 | [7 empty] | 1 | [5 empty] | 1 | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  |  | 1
21 | 1 | 1 | [16 empty] | 1 |  | 1 | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
22 |  | 1 | [16 empty] | 1 | 1 |  | 1 | 1 |  |  |  |  | 1 |  |  |  |  | 1
23 |  | 1 | [16 empty] | 1 | 1 | 1 |  | 1 |  |  |  |  | 1 |  |  |  |  | 1
24 |  | 1 | [16 empty] | 1 | 1 | 1 | 1 | [5 empty] | 1 |  |  |  |  | 1
25 | 1 |  |  | 1 |  | 1 | [17 empty] | 1 |  |  | 1 |  | 1 |  |  | 1 | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 |  |  |  | 1 |  |  | 1
26 | 1 | 1 | [9 empty] | 1 | [14 empty] | 1 | [5 empty] | 1 | [10 empty] | 1 | [45 empty] | 1
27 |  | 1 | [5 empty] | 1 | [16 empty] | 1 |  | 1 |  |  | 1 |  |  | 1
28 | [24 empty] | 1 | 1 |  | 1 |  | 1 |  |  | 1 | [16 empty] | 1 | 1
29 | [18 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 | [5 empty] | 1 | [56 empty] | 1
30 |  |  |  | 1 |  | 1 | [7 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 | 1 |  | 1 |  |  |  |  | 1 | 1 | [6 empty] | 1
31 | 1 | [6 empty] | 1 | [16 empty] | 1 | 1 | 1 | [5 empty] | 1
32 | [11 empty] | 1 | 1 | [11 empty] | 1 |  |  | 1 |  |  |  | 1 | 1 | [56 empty] | 1
33 | [11 empty] | 1 | 1 | [11 empty] | 1 |  |  | 1 |  |  | 1 |  | 1 | [56 empty] | 1
34 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
35 | [32 empty] | 1 | [15 empty] | 1
36 | [27 empty] | 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1
37 |  |  |  | 1 |  | 1 | [7 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 1 |  |  |  | 1 |  |  | 1
38 | [27 empty] | 1 |  |  |  |  | 1 |  |  | 1 | 1
39 | [27 empty] | 1 |  |  |  |  | 1 |  | 1 | 1 |  | 1
40 | [27 empty] | 1 |  |  |  |  | 1 | [5 empty] | 1
41 | [27 empty] | 1 |  |  |  |  | 1 | [6 empty] | 1
42 |  |  |  | 1 | [19 empty] | 1 |  |  | 1 | [5 empty] | 1 | 1 | [14 empty] | 1
43 | [5 empty] | 1 | [5 empty] | 1 | 1 | 1 | [9 empty] | 1 | 1 |  | 1 |  | 1 |  |  |  | 1 | [9 empty] | 1 | 1 | 1 | 1 |  | 1 | 1
44 | [32 empty] | 1 | [14 empty] | 1
45 | [8 empty] | 1 |  | 1 | 1 | [12 empty] | 1 | [7 empty] | 1 | [11 empty] | 1
46 | [32 empty] | 1 | [10 empty] | 1
47 | [5 empty] | 1 | [7 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1 | 1 | [7 empty] | 1
48 | [11 empty] | 1 | 1 | [19 empty] | 1 | [11 empty] | 1 | [13 empty] | 1 | [24 empty] | 1 | [6 empty] | 1
49 | [13 empty] | 1 | [18 empty] | 1 | [8 empty] | 1 | 1
50 | [13 empty] | 1 | 1 | 1 | [16 empty] | 1
51 | 1 | 1 | [24 empty] | 1 | [5 empty] | 1 | [18 empty] | 1 | 1 | 1
52 | [26 empty] | 1 | 1 |  |  |  |  | 1 | [18 empty] | 1 | 1 | 1
53 | [26 empty] | 1 | [5 empty] | 1 | [17 empty] | 1 |  | 1 | 1
54 | [26 empty] | 1 | [5 empty] | 1 | [17 empty] | 1 | 1 |  | 1
55 | [26 empty] | 1 | 1 |  |  |  |  | 1 | [17 empty] | 1 | 1 | 1
56 | [27 empty] | 1 |  |  |  |  | 1 | [22 empty] | 1 |  | 1 | [6 empty] | 1
57 | [27 empty] | 1 |  |  |  |  | 1 | [21 empty] | 1 |  | 1 | [6 empty] | 1
58 | [26 empty] | 1 | [5 empty] | 1 | [22 empty] | 1
59 | [26 empty] | 1 | [5 empty] | 1 | [21 empty] | 1 | [9 empty] | 1
60 | [8 empty] | 1 | 1 | 1 | [21 empty] | 1
61 | [32 empty] | 1
62 | [32 empty] | 1
63 | [32 empty] | 1
64 | 1 | 1 | [22 empty] | 1 |  | 1 | [5 empty] | 1
65 | [32 empty] | 1
66 | [32 empty] | 1 | [24 empty] | 1 | [36 empty] | 1
67 | [17 empty] | 1 | [14 empty] | 1 | [57 empty] | 1 |  |  |  |  | 1
68 | [32 empty] | 1 | [34 empty] | 1 | 1 | 1
69 | [32 empty] | 1 | [33 empty] | 1
70 | [32 empty] | 1 | [33 empty] | 1 | 1 |  | 1
71 | [32 empty] | 1 | [33 empty] | 1 | 1 | 1
72 | 1 | [31 empty] | 1 | [38 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
73 | 1 | [31 empty] | 1 | [37 empty] | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
74 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
75 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
76 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
77 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
78 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
79 | 1 | 1 | [30 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
80 | 1 | [23 empty] | 1 | [7 empty] | 1 | [16 empty] | 1 | 1 | [19 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
81 | [32 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | 1 | [10 empty] | 1 | 1 |  |  |  | 1
82 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | [10 empty] | 1 | 1 |  |  |  | 1
83 | 1 | [31 empty] | 1 | [37 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [11 empty] | 1 | 1 |  |  |  | 1
84 | [32 empty] | 1
85 | [32 empty] | 1
86 | [32 empty] | 1
87 | [32 empty] | 1
88 | [32 empty] | 1
89 | [25 empty] | 1 |  |  |  | 1 | 1 | 1 | 1
90 | [25 empty] | 1 |  |  |  | 1 | 1 | 1 | 1 | [56 empty] | 1
91 | [32 empty] | 1 | [55 empty] | 1
92 | [9 empty] | 1 |  | 1 | [20 empty] | 1
93 | [32 empty] | 1
94 | 1 | [31 empty] | 1
95 | 1 | [31 empty] | 1
96 | [32 empty] | 1
97 | [32 empty] | 1
98 | [32 empty] | 1 | [52 empty] | y | [10 empty] | 1
99 | 1 | [31 empty] | 1 | [59 empty] | 1 | 1

## stakeholder list
S_ID | Sector | Category test
S_1 | Industry | Food
S_2 | Industry | Beverage
S_3 | Industry | Food
S_4 | Professional, administration and support services | Consultancy
S_5 | Industry | Beverage
S_6 | No-profit institution | Professional Association
S_7 | Professional, administration and support services | Customer services
S_8 | Professional, administration and support services | ARUP
S_9 | Health care | Ashlawn Nursing Home
S_10 | Professional, administration and support services | Auralab
S_12 | Utility | Water provider
S_14 | Utility | Water provider
S_15 | Utility | Water provider
S_16 | Sport Facilities | Ballyshannon Leisure Centre
S_19 | Agriculture | Birchfield Farm
S_20 | Professional, administration and support services | Consultancy
S_21 | Hospitality | Black Boy Inn
S_22 | Utility | Water provider
S_23 | Agriculture | Blaen Eidda Ysbyty Ifan
S_24 | General Government | Local authority
S_25 | Education | Higher Education
S_26 | Industry | Mining
S_27 | Health care | Hospital
S_28 | Utility | Water provider
S_29 | Industry | Plumbing and heating
S_30 | Hospitality | Brandon House Hotel
S_31 | Professional, administration and support services | Consultancy
S_32 | Sport Facilities | Leisure Centre
S_33 | No-profit institution | Charity
S_34 | Sport Facilities | Leisure Centre
S_36 | Sport Facilities | Leisure Centre
S_37 | Education | Higher Education
S_38 | General Government | Local authority
S_39 | Education | Higher Education
S_40 | Professional, administration and support services | Consultancy
S_41 | Education | Higher Education
S_42 | Sport Facilities | Leisure Centre
S_43 | No-profit institution | Agency
S_44 | Professional, administration and support services | Consultancy
S_45 | General Government | Government agency
S_46 | General Government | Government agency
S_47 | General Government | Government agency
S_48 | Utility | Water provider
S_49 | Agriculture | Farm
S_50 | Utility | Water provider
S_51 | General Government | Approved Housing Body
S_52 | Sport Facilities | Leisure Centre
S_53 | Sport Facilities | Leisure Centre
S_54 | Sport Facilities | Leisure Centre
S_55 | Industry | Dairy
S_56 | Utility | Water provider
S_57 | Professional, administration and support services | Consultancy
S_58 | Industry | Beverage
S_59 | General Government | Government agency
S_60 | General Government | Local authority
S_61 | Industry | Dairy
S_62 | Education | Higher Education
S_63 | Education | Higher Education
S_64 | General Government | Local authority
S_65 | Sport Facilities | Leisure Centre
S_66 | General Government | Government department
S_67 | Professional, administration and support services | Consultancy
S_68 | Professional, administration and support services | Consultancy
S_69 | Hospitality | Café
S_70 | Hospitality | Hotel
S_71 | General Government | Local authority
S_72 | Professional, administration and support services | Consultancy
S_73 | Professional, administration and support services | Consultancy
S_74 | Utility | Water provider
S_76 | Professional, administration and support services | Consultancy
S_77 | European body | Agency
S_78 | Professional, administration and support services
S_79 | Professional, administration and support services | Consultancy
S_80 | No-profit institution | Professional Association
S_81 | Professional, administration and support services | Technology
S_82 | Utility | Energy provider
S_83 | Professional, administration and support services
S_84 | Financial and insurance activities | Risk management
S_85 | General Government | Local authority
S_86 | Education | Higher Education
S_87 | Professional, administration and support services | Consultancy
S_88 | General Government | Local authority
S_89 | Professional, administration and support services | Consultancy
S_90 | Constrution | Building company
S_91 | Constrution | Building materials
S_92 | Utility | Energy provider
S_93 | Households | General public
S_95 | Education | Higher Education
S_96 | Professional, administration and support services | Consultancy
S_97 | Sport Facilities | Leisure Centre
S_98 | Utility | Water provider
S_99 | Professional, administration and support services | Consultancy
S_100 | Professional, administration and support services | Consultancy
S_101 | Financial and insurance activities | Consultancy
S_102 | Utility | Water provider
S_103 | General Government | Statuatory body
S_104 | Retailing | Book shop
S_105 | Agriculture | Support service
S_106 | General Government | Agency
S_107 | Education | Higher Education
S_108 | Hospitality | Hotel
S_109 | Hospitality | Hotel
S_110 | Industry | Manufacturing
S_111 | Hospitality | Hotel
S_112 | General Government | Agency
S_113 | General Government | Agency
S_114 | Transport | Company
S_115 | Utility | Water provider
S_116 | Professional, administration and support services | Consultancy
S_117 | General Government | Local authority
S_118 | Utility | Water provider
S_119 | Utility | Water provider
S_120 | General Government | Local authority
S_121 | General Government | Local authority
S_122 | Utility | Water provider
S_123 | Utility | Water provider
S_124 | Entertainment | Heritage site
S_125 | Hospitality | Hotel
S_126 | General Government | Local authority
S_127 | Professional, administration and support services | Consultancy
S_128 | Professional, administration and support services | Technology
S_129 | Utility | Water provider
S_130 | General Government | Local authority
S_131 | Education | Higher Education
S_132 | Professional, administration and support services | Business support
S_133 | Utility | Water provider
S_134 | Utility | Water provider
S_135 | Utility | Water provider
S_136 | General Government | Agency
S_137 | Utility | Water provider
S_138 | Education | Higher Education
S_139 | No-profit institution | Charity
S_140 | No-profit institution | Charity
S_141 | Sport Facilities | Leisure Centre
S_142 | Hospitality | Hotel
S_144 | Professional, administration and support services | Consultancy
S_145 | Professional, administration and support services | Consultancy
S_146 | Sport Facilities | Leisure Centre
S_147 | Professional, administration and support services | Consultancy
S_148 | Education | Higher Education
S_149 | Professional, administration and support services | Consultancy
S_150 | Professional, administration and support services | Consultancy
S_151 | Professional, administration and support services | Technology
S_152 | Agriculture | Farm
S_153 | Sport Facilities | Leisure Centre
S_154 | Utility | Water provider
S_155 | Industry | Beverage
S_156 | Sport Facilities | Leisure Centre
S_157 | Sport Facilities | Leisure Centre
S_158 | Industry | Beverage
S_159 | Industry | Manufacturing
S_160 | Professional, administration and support services | Technology
S_162 | Sport Facilities | Leisure Centre
S_163 | General Government | Local authority
S_164 | Professional, administration and support services | Consultancy
S_165 | Sport Facilities | Leisure Centre
S_166 | Professional, administration and support services | Consultancy
S_167 | Industry | Oil
S_168 | Sport Facilities | Leisure Centre
S_169 | Sport Facilities | Leisure Centre
S_170 | Industry | Manufacturing
S_171 | Industry | Technology
S_172 | General Government | Agency
S_174 | Education | Higher Education
S_175 | General Government | Agency
S_176 | Professional, administration and support services | Tourism
S_177 | Hospitality | Hotel
S_178 | Hospitality | Hotel
S_179 | Hospitality | Accommodation
S_180 | No-profit institution | Community
S_181 | Education | Higher Education
S_182 | Hospitality | Hotel
S_183 | Hospitality | Hotel
S_184 | Education | Higher Education
S_185 | Hospitality | Hotel
S_186 | Hospitality | Hotel
S_187 | No-profit institution | Community
S_188 | No-profit institution | Charity
S_189 | Hospitality | Hotel
S_190 | Hospitality | Accommodation
S_191 | Education | Higher Education
S_192 | Sport Facilities | Leisure Centre
S_193 | Sport Facilities | Leisure Centre
S_194 | General Government | Local authority
S_196 | Education | Higher Education
S_197 | Education | Higher Education
S_198 | Education | Higher Education
S_199 | Education | Higher Education
S_200 | Education | Higher Education
S_201 | Education | Higher Education
S_202 | Professional, administration and support services | Consultancy
S_203 | Professional, administration and support services | Consultancy
S_204 | Households | General public
S_205 | Utility | Water provider
S_206 | No-profit institution | Network
S_207 | Professional, administration and support services | Business support
S_208 | Professional, administration and support services | Consultancy
S_209 | Constrution | Infrastructure
S_210 | General Government | Local authority
S_211 | General Government | Agency
S_212 | No-profit institution | Advocacy
S_213 | General Government | Government department
S_214 | General Government | Government department
S_215 | Professional, administration and support services | Consultancy
S_216 | General Government | Local authority
S_217 | General Government | Local authority
S_218 | General Government | Local authority
S_219 | No-profit institution | Voluntary organisation
S_220 | Hospitality | Hotel
S_221 | Education | Higher Education
S_222 | Professional, administration and support services | Consultancy
S_223 | No-profit institution | Community
S_224 | Utility | Energy provider
S_225 | Professional, administration and support services | Consultancy
S_226 | Industry | Beverage
S_161 | Education | Primary Education
S_35 | Education | Primary Education
S_173 | Education | Primary Education
S_13 | Education | Primary Education
S_143 | Education | Secondary education
S_75 | No-profit institution | Charity
S_11 | Utility | Water provider
S_94 | Hospitality | Pub
S_227 | Utility | Water provider
S_228 | Utility | Water provider
S_229 | Utility | Water provider
S_230 | Utility | Water provider
S_231 | Utility | Water provider
S_232 | Utility | Water provider
S_233 | Utility | Water provider
S_18 | Hospitality | Bangor University St Mary's Student Accommodation
S_234 | Sport Facilities | Leisure Centre
S_235
S_236